## LEGEND & SUMMARY
PMO 02 - Resource Allocation & Timesheet Monitoring Agent ¦ Mock Dataset
Input for an agent that standardizes RA + Timesheet into a member-project-week view, flags overbook/idle, compares planned RA% vs actual logged hours, and excludes valid edge cases (leave/holiday/training/approved OT). Shared masters (members, projects) are identical to the PMO 01 file. Watch for one DUPLICATED RA row (do not double-count) and members with missing weeks (onboarding).
Sheet | Grain (1 row =) | Field | Type | Example | Description
DS01_Resource_Allocation | 1 member x project allocation (the plan) | Member_ID | String | EMP-004 | Member (FK -> Member_Master).
|  | Project_ID | String | PRJ-002 | Project (FK -> Project_Master).
|  | Role | Enum | BE | Role code on this allocation.
|  | Allocation_pct | Float | 0.45 | Planned RA% (share of standard week).
|  | Start_date | Date | 2026-06-29 | Allocation start.
|  | End_date | Date | 2026-08-07 | Allocation end.
|  | Weekly_planned_hours | Float | 18.0 | allocation_pct x member's std week (PT-aware!).
DS02_Timesheet_Log | 1 member x day x project log | Member_ID | String | EMP-004 | Member (FK).
|  | Project_ID | String | PRJ-002 | Project (NULL = internal/training).
|  | Work_date | Date | 2026-07-07 | Work date.
|  | Logged_hours | Float | 6.5 | Hours logged that day.
|  | Log_category | Enum | Project | Project/Internal/Training/Admin.
|  | Task_ref | String | TASK-007 | Optional task reference (may be NULL).
DS03_Overbook_Idle_Config | 1 threshold rule (read as rule engine) | Config_ID | String | CFG-001 | Config id.
|  | Rule_name | String | SETA-08-SOP-001 | Rule set name.
|  | Overbook_threshold | Float | 1.10 | Busy > this -> Overbooked (Yellow).
|  | Overbook_red_threshold | Float | 1.20 | Busy > this -> Overbooked (Red).
|  | Idle_threshold | Float | 0.75 | Busy < this -> Idle (aligned to SOP, not 0.20).
|  | Mismatch_pct_threshold | Float | 0.20 | ¦logged-planned¦/planned > this -> mismatch.
|  | OT_max_hours_per_week | Float | 48.0 | Above this/week = OT to review.
|  | Effective_date | Date | 2026-01-01 | Effective date.
DS04_Leave_Holiday_Records | 1 leave-day of a member (or a company holiday) | Record_ID | String | LV-0002 | Record id.
|  | Member_ID | String | EMP-003 | Member (NULL = company-wide holiday).
|  | Leave_date | Date | 2026-07-06 | Date.
|  | Leave_type | Enum | Annual Leave | Annual/Sick/Maternity/Public Holiday/Training/Approved OT Comp.
|  | Approved | Bool | TRUE | TRUE = approved.
|  | Duration_days | Float | 1.0 | Days (0.5 = half day).
|  | Note | String | Full week leave | Note.
DS05_Project_Master | 1 project | Project_ID | String | PRJ-002 | Project id.
|  | Project_name | String | Energent AI | Name.
|  | Account_ID | String | ACC-B | Account/client group.
|  | Project_type | String | AI/ML Platform | Type.
|  | Status | Enum | Active | Active/On Hold/Completed/Cancelled.
|  | PM_ID | String | EMP-012 | PM (FK -> Member_Master).
|  | Start_date | Date | 2026-04-06 | Start.
|  | End_date | Date | 2026-12-31 | Planned end.
DS06_Member_Master | 1 member | Member_ID | String | EMP-009 | Member id.
|  | Full_name | String | Ly Van Minh | Name.
|  | Department | String | Frontend | Department.
|  | Role_title | String | Frontend Developer | Title.
|  | Level | String | L2 | Level L1-L7.
|  | Line_manager_id | String | EMP-004 | Manager (FK).
|  | Employment_status | Enum | Probation | Active/Probation/On Leave/Resigned.
|  | Employment | Enum | FT | FT/PT.
|  | Std_hours_week | Float | 40 | Standard hours/week (PT = 20).
|  | Join_date | Date | 2026-07-14 | Join date (drives onboarding edge).
REF_Calendar_Weeks [SHARED/REF] | 1 week of the monitoring window | Week_ID | String | W3 | Week id.
|  | Week_start | Date | 2026-07-13 | Monday.
|  | Working_days | Int | 4 | Working days (holiday reduces this).
|  | Holiday_hours_ft | Float | 8 | FT hours lost to holidays that week.
REF_KPI_Norms [SHARED/REF] | 1 RAG metric threshold (SETA-08-SOP-001) | Norm_ID | String | N01 | Norm id.
|  | Metric | String | Busy Rate | Metric.
|  | Green/Yellow/Red | String | 85-110% / ... | RAG thresholds.
Answer_Key [ANSWER KEY] | 1 finding the agent should detect (Problem 2) | Finding_ID | String | F-07 | Finding id.
|  | Entity_id | String | EMP-004 | Member/week.
|  | Issue_type | String | Overbook | Category.
|  | Expected_detection | String | Busy 125% -> rebalance | What to detect.
|  | Severity | String | High | Severity.

## DS03_Overbook_Idle_Config
Config_ID | Rule_name | Overbook_threshold | Overbook_red_threshold | Idle_threshold | Mismatch_pct_threshold | OT_max_hours_per_week | Effective_date
CFG-001 | SETA-08-SOP-001 RAG thresholds | 1.1 | 1.2 | 0.75 | 0.2 | 48 | 2026-01-01

## REF_Calendar_Weeks
Week_ID | Week_start | Week_end | Working_days | Holiday_hours_ft | Note
W1 | 2026-06-29 | 2026-07-03 | 5 | 0
W2 | 2026-07-06 | 2026-07-10 | 5 | 0
W3 | 2026-07-13 | 2026-07-17 | 4 | 8 | Company public holiday Mon 2026-07-13 → 4 working days
W4 | 2026-07-20 | 2026-07-24 | 5 | 0
W5 | 2026-07-27 | 2026-07-31 | 5 | 0
W6 | 2026-08-03 | 2026-08-07 | 5 | 0

## REF_KPI_Norms
Norm_ID | Metric | Formula | Green | Yellow | Red | Used_for
N01 | Busy Rate | Planned_h / Available_h | 85-110% | 111-119% | >120% or <75% | Overbook/Idle — Problem 2 + feasibility Problem 1
N02 | Utilization Rate | Worked_h / Available_h | 75-90% | 60-74% / 91-100% | <60% or >100% | Real intensity; >100% burnout — Problem 2
N03 | Billable Rate | Billable_h / Worked_h | >=80% | 70-79% | <70% | Revenue-generating hours — Problem 2
N04 | Bench Rate | Bench_h / Available_h | <=10% | 11-20% | >20% | Unassigned capacity — Problem 2 (idle)
N05 | Overtime Ratio | OT_h / Standard_h | <=5% | 6-15% | >15% | Leading burnout — Problem 2 (OT edge)
N06 | Effort Consumption | Actual_h / Planned_h | 85-110% | 75-84% / 111-119% | <=75% or >=120% | RA vs Timesheet mismatch — Problem 2 + Problem 1
N07 | On-time Delivery | On-time_MS / Total_MS | >=90% | 70-89% | <70% | Benchmark feasibility — Problem 1
N08 | SPI | EV / PV | 0.95-1.05 | 0.85-0.94 / 1.06-1.15 | <0.85 or >1.15 | Schedule realism — Problem 1
N09 | Velocity Variance | StdDev(5 sprint)/Avg | <=15% | 16-25% | >25% | Forecast reliability — Problem 1
N10 | THI | Non-dev_h / Total_h | 15-25% | 10-14% / 26-35% | <10% or >35% | Tech-debt prevention budget — Problem 1
N11 | Risk Closure Rate | Risks_closed / Total | >=80% | 60-79% | <60% | Whether RAID is alive — Problem 1
N12 | Training Compliance | Done / Required | 100% | 85-99% | <85% | Valid edge case (training) — Problem 2

## DS01_Resource_Allocation
project_id | MEMBER_ID | Allocation_pct | role | END_DATE | start_date | weekly_planned_hours
PRJ-001 | EMP-001 | 0.6 | BE | 2026-08-07 | 2026-06-29 | 24
PRJ-003 | EMP-001 | 0.55 | BE | 2026-08-07 | 2026-06-29 | 22
PRJ-002 | EMP-002 | 0.9 | DE | 2026-08-07 | 2026-06-29 | 36
PRJ-002 | EMP-003 | 1 | ML | 2026-08-07 | 2026-06-29 | 40
PRJ-001 | EMP-004 | 0.8 | BE | 2026-08-07 | 2026-06-29 | 32
PRJ-002 | EMP-004 | 0.45 | BE | 2026-08-07 | 2026-06-29 | 18
PRJ-001 | EMP-005 | 0.3 | DevOps | 2026-08-07 | 2026-06-29 | 12
PRJ-002 | EMP-005 | 0.3 | DevOps | 2026-08-07 | 2026-06-29 | 12
PRJ-001 | EMP-006 | 0.95 | Sec | 2026-08-07 | 2026-06-29 | 38
PRJ-002 | EMP-007 | 0.8 | Design | 2026-08-07 | 2026-06-29 | 16
PRJ-002 | EMP-008 | 0.5 | BA | 2026-08-07 | 2026-06-29 | 20
PRJ-002 | EMP-009 | 0.8 | FE | 2026-08-07 | 2026-07-13 | 32
PRJ-001 | EMP-010 | 0.6 | QA | 2026-08-07 | 2026-06-29 | 24
PRJ-002 | EMP-010 | 0.5 | QA | 2026-08-07 | 2026-06-29 | 20
PRJ-002 | EMP-010 | 0.5 | QA | 2026-08-07 | 2026-06-29 | 20
PRJ-103 | EMP-103 | 0.86 | BE | 2026-08-07 | 2026-06-29 | 34.4
PRJ-102 | EMP-104 | 0.85 | BA | 2026-08-07 | 2026-06-29 | 34
PRJ-106 | EMP-105 | 0.86 | DevOps | 2026-08-07 | 2026-06-29 | 34.4
PRJ-103 | EMP-106 | 1.01 | FE | 2026-08-07 | 2026-06-29 | 40.4
PRJ-104 | EMP-107 | 0.45 | DE | 2026-08-07 | 2026-06-29 | 18
PRJ-102 | EMP-107 | 0.5 | DE | 2026-08-07 | 2026-06-29 | 20
PRJ-102 | EMP-108 | 0.53 | FE | 2026-08-07 | 2026-06-29 | 21.2
PRJ-103 | EMP-108 | 0.39 | FE | 2026-08-07 | 2026-06-29 | 15.6
PRJ-108 | EMP-109 | 0.96 | DevOps | 2026-08-07 | 2026-06-29 | 38.4
PRJ-101 | EMP-110 | 0.56 | FE | 2026-08-07 | 2026-06-29 | 22.4
PRJ-105 | EMP-110 | 0.42 | FE | 2026-08-07 | 2026-06-29 | 16.8
PRJ-105 | EMP-111 | 1.04 | BA | 2026-08-07 | 2026-06-29 | 41.6
PRJ-105 | EMP-112 | 0.44 | BA | 2026-08-07 | 2026-06-29 | 17.6
PRJ-102 | EMP-112 | 0.6 | BA | 2026-08-07 | 2026-06-29 | 24
PRJ-106 | EMP-113 | 0.86 | BE | 2026-08-07 | 2026-06-29 | 17.2
PRJ-102 | EMP-114 | 0.43 | Design | 2026-08-07 | 2026-06-29 | 8.6
PRJ-108 | EMP-114 | 0.48 | Design | 2026-08-07 | 2026-06-29 | 9.6
PRJ-102 | EMP-115 | 0.6 | Design | 2026-08-07 | 2026-06-29 | 24
PRJ-105 | EMP-115 | 0.32 | Design | 2026-08-07 | 2026-06-29 | 12.8
PRJ-105 | EMP-116 | 0.49 | QA | 2026-08-07 | 2026-06-29 | 19.6
PRJ-104 | EMP-116 | 0.49 | QA | 2026-08-07 | 2026-06-29 | 19.6
PRJ-102 | EMP-117 | 0.49 | ML | 2026-08-07 | 2026-06-29 | 19.6
PRJ-106 | EMP-117 | 0.55 | ML | 2026-08-07 | 2026-06-29 | 22
PRJ-101 | EMP-118 | 0.48 | Design | 2026-08-07 | 2026-06-29 | 19.2
PRJ-105 | EMP-118 | 0.61 | Design | 2026-08-07 | 2026-06-29 | 24.4

## DS02_Timesheet_Log
work_date | member_id | PROJECT_ID | logged_hours | LOG_CATEGORY | task_ref
2026-06-29 | EMP-001 | PRJ-001 | 4.5 | Project
2026-06-29 | EMP-001 | PRJ-003 | 4 | Project
2026-06-30 | EMP-001 | PRJ-001 | 4.5 | Project
2026-06-30 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-01 | EMP-001 | PRJ-001 | 5 | Project
2026-07-01 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-02 | EMP-001 | PRJ-001 | 5 | Project
2026-07-02 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-03 | EMP-001 | PRJ-001 | 5 | Project
2026-07-03 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-06 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-06 | EMP-001 | PRJ-003 | 4 | Project
2026-07-07 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-07 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-08 | EMP-001 | PRJ-001 | 5 | Project
2026-07-08 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-09 | EMP-001 | PRJ-001 | 5 | Project
2026-07-09 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-10 | EMP-001 | PRJ-001 | 5 | Project
2026-07-10 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-14 | EMP-001 | PRJ-001 | 5 | Project
2026-07-14 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-15 | EMP-001 | PRJ-001 | 5 | Project
2026-07-15 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-16 | EMP-001 | PRJ-001 | 5 | Project
2026-07-16 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-17 | EMP-001 | PRJ-001 | 5 | Project
2026-07-17 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-20 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-20 | EMP-001 | PRJ-003 | 4 | Project
2026-07-21 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-21 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-22 | EMP-001 | PRJ-001 | 5 | Project
2026-07-22 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-23 | EMP-001 | PRJ-001 | 5 | Project
2026-07-23 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-24 | EMP-001 | PRJ-001 | 5 | Project
2026-07-24 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-27 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-27 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-28 | EMP-001 | PRJ-001 | 4.5 | Project
2026-07-28 | EMP-001 | PRJ-003 | 4.5 | Project
2026-07-29 | EMP-001 | PRJ-001 | 5 | Project
2026-07-29 | EMP-001 | PRJ-003 | 5 | Project
2026-07-30 | EMP-001 | PRJ-001 | 5 | Project
2026-07-30 | EMP-001 | PRJ-003 | 5 | Project
2026-07-31 | EMP-001 | PRJ-001 | 5 | Project
2026-07-31 | EMP-001 | PRJ-003 | 5 | Project
2026-08-03 | EMP-001 | PRJ-001 | 4.5 | Project
2026-08-03 | EMP-001 | PRJ-003 | 4.5 | Project
2026-08-04 | EMP-001 | PRJ-001 | 4.5 | Project
2026-08-04 | EMP-001 | PRJ-003 | 4.5 | Project
2026-08-05 | EMP-001 | PRJ-001 | 5 | Project
2026-08-05 | EMP-001 | PRJ-003 | 5 | Project
2026-08-06 | EMP-001 | PRJ-001 | 5 | Project
2026-08-06 | EMP-001 | PRJ-003 | 5 | Project
2026-08-07 | EMP-001 | PRJ-001 | 5 | Project
2026-08-07 | EMP-001 | PRJ-003 | 5 | Project
2026-06-29 | EMP-002 | PRJ-002 | 4 | Project
2026-06-30 | EMP-002 | PRJ-002 | 4 | Project
2026-07-01 | EMP-002 | PRJ-002 | 4 | Project
2026-07-02 | EMP-002 | PRJ-002 | 4 | Project
2026-07-03 | EMP-002 | PRJ-002 | 4 | Project
2026-07-06 | EMP-002 | PRJ-002 | 4 | Project
2026-07-07 | EMP-002 | PRJ-002 | 3.5 | Project
2026-07-08 | EMP-002 | PRJ-002 | 3.5 | Project
2026-07-09 | EMP-002 | PRJ-002 | 3.5 | Project
2026-07-10 | EMP-002 | PRJ-002 | 3.5 | Project
2026-07-14 | EMP-002 | PRJ-002 | 4 | Project
2026-07-15 | EMP-002 | PRJ-002 | 4 | Project
2026-07-16 | EMP-002 | PRJ-002 | 4 | Project
2026-07-17 | EMP-002 | PRJ-002 | 4 | Project
2026-07-20 | EMP-002 | PRJ-002 | 4 | Project
2026-07-21 | EMP-002 | PRJ-002 | 4 | Project
2026-07-22 | EMP-002 | PRJ-002 | 4 | Project
2026-07-23 | EMP-002 | PRJ-002 | 4 | Project
2026-07-24 | EMP-002 | PRJ-002 | 4 | Project
2026-07-27 | EMP-002 | PRJ-002 | 4 | Project
2026-07-28 | EMP-002 | PRJ-002 | 4 | Project
2026-07-29 | EMP-002 | PRJ-002 | 4 | Project
2026-07-30 | EMP-002 | PRJ-002 | 4 | Project
2026-07-31 | EMP-002 | PRJ-002 | 4 | Project
2026-08-03 | EMP-002 | PRJ-002 | 4 | Project
2026-08-04 | EMP-002 | PRJ-002 | 3.5 | Project
2026-08-05 | EMP-002 | PRJ-002 | 3.5 | Project
2026-08-06 | EMP-002 | PRJ-002 | 3.5 | Project
2026-08-07 | EMP-002 | PRJ-002 | 3.5 | Project
2026-06-29 | EMP-003 | PRJ-002 | 8 | Project
2026-06-30 | EMP-003 | PRJ-002 | 8 | Project
2026-07-01 | EMP-003 | PRJ-002 | 8 | Project
2026-07-02 | EMP-003 | PRJ-002 | 8 | Project
2026-07-03 | EMP-003 | PRJ-002 | 8 | Project
2026-07-14 | EMP-003 | PRJ-002 | 6 | Project
2026-07-15 | EMP-003 | PRJ-002 | 6 | Project
2026-07-16 | EMP-003 | PRJ-002 | 6 | Project
2026-07-17 | EMP-003 | PRJ-002 | 6 | Project
2026-07-20 | EMP-003 | PRJ-002 | 8 | Project
2026-07-21 | EMP-003 | PRJ-002 | 8 | Project
2026-07-22 | EMP-003 | PRJ-002 | 8 | Project
2026-07-23 | EMP-003 | PRJ-002 | 8 | Project
2026-07-24 | EMP-003 | PRJ-002 | 8 | Project
2026-07-27 | EMP-003 | PRJ-002 | 10 | Project
2026-07-28 | EMP-003 | PRJ-002 | 10.5 | Project
2026-07-29 | EMP-003 | PRJ-002 | 10.5 | Project
2026-07-30 | EMP-003 | PRJ-002 | 10.5 | Project
2026-07-31 | EMP-003 | PRJ-002 | 10.5 | Project
2026-08-03 | EMP-003 | PRJ-002 | 8 | Project
2026-08-04 | EMP-003 | PRJ-002 | 8 | Project
2026-08-05 | EMP-003 | PRJ-002 | 8 | Project
2026-08-06 | EMP-003 | PRJ-002 | 8 | Project
2026-08-07 | EMP-003 | PRJ-002 | 8 | Project
2026-06-29 | EMP-004 | PRJ-001 | 6 | Project
2026-06-29 | EMP-004 | PRJ-002 | 4 | Project
2026-06-30 | EMP-004 | PRJ-001 | 6.5 | Project
2026-06-30 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-01 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-01 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-02 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-02 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-03 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-03 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-06 | EMP-004 | PRJ-001 | 6 | Project
2026-07-06 | EMP-004 | PRJ-002 | 4 | Project
2026-07-07 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-07 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-08 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-08 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-09 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-09 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-10 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-10 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-14 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-14 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-15 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-15 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-16 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-16 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-17 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-17 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-20 | EMP-004 | PRJ-001 | 6 | Project
2026-07-20 | EMP-004 | PRJ-002 | 4 | Project
2026-07-21 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-21 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-22 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-22 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-23 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-23 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-24 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-24 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-27 | EMP-004 | PRJ-001 | 6 | Project
2026-07-27 | EMP-004 | PRJ-002 | 4 | Project
2026-07-28 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-28 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-29 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-29 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-30 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-30 | EMP-004 | PRJ-002 | 3.5 | Project
2026-07-31 | EMP-004 | PRJ-001 | 6.5 | Project
2026-07-31 | EMP-004 | PRJ-002 | 3.5 | Project
2026-08-03 | EMP-004 | PRJ-001 | 6 | Project
2026-08-03 | EMP-004 | PRJ-002 | 4 | Project
2026-08-04 | EMP-004 | PRJ-001 | 6.5 | Project
2026-08-04 | EMP-004 | PRJ-002 | 3.5 | Project
2026-08-05 | EMP-004 | PRJ-001 | 6.5 | Project
2026-08-05 | EMP-004 | PRJ-002 | 3.5 | Project
2026-08-06 | EMP-004 | PRJ-001 | 6.5 | Project
2026-08-06 | EMP-004 | PRJ-002 | 3.5 | Project
2026-08-07 | EMP-004 | PRJ-001 | 6.5 | Project
2026-08-07 | EMP-004 | PRJ-002 | 3.5 | Project
2026-06-29 | EMP-005 | PRJ-001 | 2 | Project
2026-06-29 | EMP-005 | PRJ-002 | 2 | Project
2026-06-30 | EMP-005 | PRJ-001 | 2.5 | Project
2026-06-30 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-01 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-01 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-02 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-02 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-03 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-03 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-06 | EMP-005 | PRJ-001 | 2 | Project
2026-07-06 | EMP-005 | PRJ-002 | 2 | Project
2026-07-07 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-07 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-08 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-08 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-09 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-09 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-10 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-10 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-14 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-14 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-15 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-15 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-16 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-16 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-17 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-17 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-20 | EMP-005 | PRJ-001 | 2 | Project
2026-07-20 | EMP-005 | PRJ-002 | 2 | Project
2026-07-21 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-21 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-22 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-22 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-23 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-23 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-24 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-24 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-27 | EMP-005 | PRJ-001 | 2 | Project
2026-07-27 | EMP-005 | PRJ-002 | 2 | Project
2026-07-28 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-28 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-29 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-29 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-30 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-30 | EMP-005 | PRJ-002 | 2.5 | Project
2026-07-31 | EMP-005 | PRJ-001 | 2.5 | Project
2026-07-31 | EMP-005 | PRJ-002 | 2.5 | Project
2026-08-03 | EMP-005 | PRJ-001 | 2 | Project
2026-08-03 | EMP-005 | PRJ-002 | 2 | Project
2026-08-04 | EMP-005 | PRJ-001 | 2.5 | Project
2026-08-04 | EMP-005 | PRJ-002 | 2.5 | Project
2026-08-05 | EMP-005 | PRJ-001 | 2.5 | Project
2026-08-05 | EMP-005 | PRJ-002 | 2.5 | Project
2026-08-06 | EMP-005 | PRJ-001 | 2.5 | Project
2026-08-06 | EMP-005 | PRJ-002 | 2.5 | Project
2026-08-07 | EMP-005 | PRJ-001 | 2.5 | Project
2026-08-07 | EMP-005 | PRJ-002 | 2.5 | Project
2026-06-29 | EMP-006 | PRJ-001 | 10 | Project
2026-06-30 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-01 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-02 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-03 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-06 | EMP-006 | PRJ-001 | 10 | Project
2026-07-07 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-08 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-09 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-10 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-14 | EMP-006 | PRJ-001 | 10 | Project
2026-07-15 | EMP-006 | PRJ-001 | 10 | Project
2026-07-16 | EMP-006 | PRJ-001 | 10 | Project
2026-07-17 | EMP-006 | PRJ-001 | 10 | Project
2026-07-20 | EMP-006 | PRJ-001 | 10 | Project
2026-07-21 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-22 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-23 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-24 | EMP-006 | PRJ-001 | 9.5 | Project
2026-07-27 | EMP-006 | PRJ-001 | 10 | Project
2026-07-28 | EMP-006 | PRJ-001 | 10 | Project
2026-07-29 | EMP-006 | PRJ-001 | 10 | Project
2026-07-30 | EMP-006 | PRJ-001 | 10 | Project
2026-07-31 | EMP-006 | PRJ-001 | 10 | Project
2026-08-03 | EMP-006 | PRJ-001 | 10 | Project
2026-08-04 | EMP-006 | PRJ-001 | 9.5 | Project
2026-08-05 | EMP-006 | PRJ-001 | 9.5 | Project
2026-08-06 | EMP-006 | PRJ-001 | 9.5 | Project
2026-08-07 | EMP-006 | PRJ-001 | 9.5 | Project
2026-06-29 | EMP-007 | PRJ-002 | 3.5 | Project
2026-06-30 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-01 | EMP-007 | PRJ-002 | 3 | Project
2026-07-02 | EMP-007 | PRJ-002 | 3 | Project
2026-07-03 | EMP-007 | PRJ-002 | 3 | Project
2026-07-06 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-07 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-08 | EMP-007 | PRJ-002 | 3 | Project
2026-07-09 | EMP-007 | PRJ-002 | 3 | Project
2026-07-10 | EMP-007 | PRJ-002 | 3 | Project
2026-07-14 | EMP-007 | PRJ-002 | 3 | Project
2026-07-15 | EMP-007 | PRJ-002 | 3 | Project
2026-07-16 | EMP-007 | PRJ-002 | 3 | Project
2026-07-17 | EMP-007 | PRJ-002 | 3 | Project
2026-07-20 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-21 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-22 | EMP-007 | PRJ-002 | 3 | Project
2026-07-23 | EMP-007 | PRJ-002 | 3 | Project
2026-07-24 | EMP-007 | PRJ-002 | 3 | Project
2026-07-27 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-28 | EMP-007 | PRJ-002 | 3.5 | Project
2026-07-29 | EMP-007 | PRJ-002 | 3 | Project
2026-07-30 | EMP-007 | PRJ-002 | 3 | Project
2026-07-31 | EMP-007 | PRJ-002 | 3 | Project
2026-08-03 | EMP-007 | PRJ-002 | 3.5 | Project
2026-08-04 | EMP-007 | PRJ-002 | 3.5 | Project
2026-08-05 | EMP-007 | PRJ-002 | 3 | Project
2026-08-06 | EMP-007 | PRJ-002 | 3 | Project
2026-08-07 | EMP-007 | PRJ-002 | 3 | Project
2026-06-29 | EMP-008 | PRJ-002 | 4 | Project
2026-06-30 | EMP-008 | PRJ-002 | 4 | Project
2026-07-01 | EMP-008 | PRJ-002 | 4 | Project
2026-07-02 | EMP-008 | PRJ-002 | 4 | Project
2026-07-03 | EMP-008 | PRJ-002 | 4 | Project
2026-07-06 | EMP-008 | PRJ-002 | 4 | Project
2026-07-07 | EMP-008 | PRJ-002 | 4 | Project
2026-07-08 | EMP-008 | PRJ-002 | 4 | Project
2026-07-09 | EMP-008 | PRJ-002 | 4 | Project
2026-07-10 | EMP-008 | PRJ-002 | 4 | Project
2026-07-14 | EMP-008 | PRJ-002 | 4 | Project
2026-07-15 | EMP-008 | PRJ-002 | 4 | Project
2026-07-16 | EMP-008 | PRJ-002 | 4 | Project
2026-07-17 | EMP-008 | PRJ-002 | 4 | Project
2026-07-20 | EMP-008 | PRJ-002 | 4 | Project
2026-07-21 | EMP-008 | PRJ-002 | 4 | Project
2026-07-22 | EMP-008 | PRJ-002 | 4 | Project
2026-07-23 | EMP-008 | PRJ-002 | 4 | Project
2026-07-24 | EMP-008 | PRJ-002 | 4 | Project
2026-07-27 | EMP-008 | PRJ-002 | 4 | Project
2026-07-28 | EMP-008 | PRJ-002 | 4 | Project
2026-07-29 | EMP-008 | PRJ-002 | 4 | Project
2026-07-30 | EMP-008 | PRJ-002 | 4 | Project
2026-07-31 | EMP-008 | PRJ-002 | 4 | Project
2026-08-03 | EMP-008 | PRJ-002 | 4 | Project
2026-08-04 | EMP-008 | PRJ-002 | 4 | Project
2026-08-05 | EMP-008 | PRJ-002 | 4 | Project
2026-08-06 | EMP-008 | PRJ-002 | 4 | Project
2026-08-07 | EMP-008 | PRJ-002 | 4 | Project
2026-07-14 | EMP-009 |  | 6 | Training
2026-07-15 | EMP-009 |  | 6 | Training
2026-07-16 | EMP-009 |  | 6 | Training
2026-07-17 | EMP-009 |  | 6 | Training
2026-07-20 | EMP-009 | PRJ-002 | 6 | Project
2026-07-21 | EMP-009 | PRJ-002 | 5.5 | Project
2026-07-22 | EMP-009 | PRJ-002 | 5.5 | Project
2026-07-23 | EMP-009 | PRJ-002 | 5.5 | Project
2026-07-24 | EMP-009 | PRJ-002 | 5.5 | Project
2026-07-27 | EMP-009 | PRJ-002 | 6 | Project
2026-07-28 | EMP-009 | PRJ-002 | 6.5 | Project
2026-07-29 | EMP-009 | PRJ-002 | 6.5 | Project
2026-07-30 | EMP-009 | PRJ-002 | 6.5 | Project
2026-07-31 | EMP-009 | PRJ-002 | 6.5 | Project
2026-08-03 | EMP-009 | PRJ-002 | 6 | Project
2026-08-04 | EMP-009 | PRJ-002 | 6.5 | Project
2026-08-05 | EMP-009 | PRJ-002 | 6.5 | Project
2026-08-06 | EMP-009 | PRJ-002 | 6.5 | Project
2026-08-07 | EMP-009 | PRJ-002 | 6.5 | Project
2026-06-29 | EMP-010 | PRJ-001 | 4.5 | Project
2026-06-29 | EMP-010 | PRJ-002 | 4 | Project
2026-06-30 | EMP-010 | PRJ-001 | 4.5 | Project
2026-06-30 | EMP-010 | PRJ-002 | 4 | Project
2026-07-01 | EMP-010 | PRJ-001 | 5 | Project
2026-07-01 | EMP-010 | PRJ-002 | 4 | Project
2026-07-02 | EMP-010 | PRJ-001 | 5 | Project
2026-07-02 | EMP-010 | PRJ-002 | 4 | Project
2026-07-03 | EMP-010 | PRJ-001 | 5 | Project
2026-07-03 | EMP-010 | PRJ-002 | 4 | Project
2026-07-06 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-06 | EMP-010 | PRJ-002 | 4 | Project
2026-07-07 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-07 | EMP-010 | PRJ-002 | 4 | Project
2026-07-08 | EMP-010 | PRJ-001 | 5 | Project
2026-07-08 | EMP-010 | PRJ-002 | 4 | Project
2026-07-09 | EMP-010 | PRJ-001 | 5 | Project
2026-07-09 | EMP-010 | PRJ-002 | 4 | Project
2026-07-10 | EMP-010 | PRJ-001 | 5 | Project
2026-07-10 | EMP-010 | PRJ-002 | 4 | Project
2026-07-14 | EMP-010 | PRJ-001 | 5 | Project
2026-07-14 | EMP-010 | PRJ-002 | 4 | Project
2026-07-15 | EMP-010 | PRJ-001 | 5 | Project
2026-07-15 | EMP-010 | PRJ-002 | 4 | Project
2026-07-16 | EMP-010 | PRJ-001 | 5 | Project
2026-07-16 | EMP-010 | PRJ-002 | 4 | Project
2026-07-17 | EMP-010 | PRJ-001 | 5 | Project
2026-07-17 | EMP-010 | PRJ-002 | 4 | Project
2026-07-20 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-20 | EMP-010 | PRJ-002 | 4 | Project
2026-07-21 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-21 | EMP-010 | PRJ-002 | 4 | Project
2026-07-22 | EMP-010 | PRJ-001 | 5 | Project
2026-07-22 | EMP-010 | PRJ-002 | 4 | Project
2026-07-23 | EMP-010 | PRJ-001 | 5 | Project
2026-07-23 | EMP-010 | PRJ-002 | 4 | Project
2026-07-24 | EMP-010 | PRJ-001 | 5 | Project
2026-07-24 | EMP-010 | PRJ-002 | 4 | Project
2026-07-27 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-27 | EMP-010 | PRJ-002 | 4 | Project
2026-07-28 | EMP-010 | PRJ-001 | 4.5 | Project
2026-07-28 | EMP-010 | PRJ-002 | 4 | Project
2026-07-29 | EMP-010 | PRJ-001 | 5 | Project
2026-07-29 | EMP-010 | PRJ-002 | 4 | Project
2026-07-30 | EMP-010 | PRJ-001 | 5 | Project
2026-07-30 | EMP-010 | PRJ-002 | 4 | Project
2026-07-31 | EMP-010 | PRJ-001 | 5 | Project
2026-07-31 | EMP-010 | PRJ-002 | 4 | Project
2026-08-03 | EMP-010 | PRJ-001 | 4.5 | Project
2026-08-03 | EMP-010 | PRJ-002 | 4 | Project
2026-08-04 | EMP-010 | PRJ-001 | 4.5 | Project
2026-08-04 | EMP-010 | PRJ-002 | 4 | Project
2026-08-05 | EMP-010 | PRJ-001 | 5 | Project
2026-08-05 | EMP-010 | PRJ-002 | 4 | Project
2026-08-06 | EMP-010 | PRJ-001 | 5 | Project
2026-08-06 | EMP-010 | PRJ-002 | 4 | Project
2026-08-07 | EMP-010 | PRJ-001 | 5 | Project
2026-08-07 | EMP-010 | PRJ-002 | 4 | Project
2026-06-29 | EMP-103 | PRJ-103 | 7.5 | Project
2026-06-30 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-01 | EMP-103 | PRJ-103 | 7 | Project
2026-07-02 | EMP-103 | PRJ-103 | 7 | Project
2026-07-03 | EMP-103 | PRJ-103 | 7 | Project
2026-07-06 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-07 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-08 | EMP-103 | PRJ-103 | 7 | Project
2026-07-09 | EMP-103 | PRJ-103 | 7 | Project
2026-07-10 | EMP-103 | PRJ-103 | 7 | Project
2026-07-14 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-15 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-16 | EMP-103 | PRJ-103 | 7 | Project
2026-07-17 | EMP-103 | PRJ-103 | 7 | Project
2026-07-20 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-21 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-22 | EMP-103 | PRJ-103 | 7 | Project
2026-07-23 | EMP-103 | PRJ-103 | 7 | Project
2026-07-24 | EMP-103 | PRJ-103 | 7 | Project
2026-07-27 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-28 | EMP-103 | PRJ-103 | 7.5 | Project
2026-07-29 | EMP-103 | PRJ-103 | 7 | Project
2026-07-30 | EMP-103 | PRJ-103 | 7 | Project
2026-07-31 | EMP-103 | PRJ-103 | 7 | Project
2026-08-03 | EMP-103 | PRJ-103 | 7.5 | Project
2026-08-04 | EMP-103 | PRJ-103 | 7.5 | Project
2026-08-05 | EMP-103 | PRJ-103 | 7 | Project
2026-08-06 | EMP-103 | PRJ-103 | 7 | Project
2026-08-07 | EMP-103 | PRJ-103 | 7 | Project
2026-06-29 | EMP-104 | PRJ-102 | 7 | Project
2026-06-30 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-01 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-02 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-03 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-06 | EMP-104 | PRJ-102 | 7 | Project
2026-07-07 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-08 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-09 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-10 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-14 | EMP-104 | PRJ-102 | 7 | Project
2026-07-15 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-16 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-17 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-20 | EMP-104 | PRJ-102 | 7 | Project
2026-07-21 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-22 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-23 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-24 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-27 | EMP-104 | PRJ-102 | 7 | Project
2026-07-28 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-29 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-30 | EMP-104 | PRJ-102 | 6.5 | Project
2026-07-31 | EMP-104 | PRJ-102 | 6.5 | Project
2026-08-03 | EMP-104 | PRJ-102 | 7 | Project
2026-08-04 | EMP-104 | PRJ-102 | 6.5 | Project
2026-08-05 | EMP-104 | PRJ-102 | 6.5 | Project
2026-08-06 | EMP-104 | PRJ-102 | 6.5 | Project
2026-08-07 | EMP-104 | PRJ-102 | 6.5 | Project
2026-06-29 | EMP-105 | PRJ-106 | 7 | Project
2026-06-30 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-01 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-02 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-03 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-06 | EMP-105 | PRJ-106 | 7 | Project
2026-07-07 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-08 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-09 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-10 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-14 | EMP-105 | PRJ-106 | 7 | Project
2026-07-15 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-16 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-17 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-20 | EMP-105 | PRJ-106 | 7 | Project
2026-07-21 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-22 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-23 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-24 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-27 | EMP-105 | PRJ-106 | 7 | Project
2026-07-28 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-29 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-30 | EMP-105 | PRJ-106 | 6.5 | Project
2026-07-31 | EMP-105 | PRJ-106 | 6.5 | Project
2026-08-03 | EMP-105 | PRJ-106 | 7 | Project
2026-08-04 | EMP-105 | PRJ-106 | 6.5 | Project
2026-08-05 | EMP-105 | PRJ-106 | 6.5 | Project
2026-08-06 | EMP-105 | PRJ-106 | 6.5 | Project
2026-08-07 | EMP-105 | PRJ-106 | 6.5 | Project
2026-06-29 | EMP-106 | PRJ-103 | 7.5 | Project
2026-06-30 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-01 | EMP-106 | PRJ-103 | 8 | Project
2026-07-02 | EMP-106 | PRJ-103 | 8 | Project
2026-07-03 | EMP-106 | PRJ-103 | 8 | Project
2026-07-06 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-07 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-08 | EMP-106 | PRJ-103 | 8 | Project
2026-07-09 | EMP-106 | PRJ-103 | 8 | Project
2026-07-10 | EMP-106 | PRJ-103 | 8 | Project
2026-07-14 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-15 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-16 | EMP-106 | PRJ-103 | 8 | Project
2026-07-17 | EMP-106 | PRJ-103 | 8 | Project
2026-07-20 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-21 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-22 | EMP-106 | PRJ-103 | 8 | Project
2026-07-23 | EMP-106 | PRJ-103 | 8 | Project
2026-07-24 | EMP-106 | PRJ-103 | 8 | Project
2026-07-27 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-28 | EMP-106 | PRJ-103 | 7.5 | Project
2026-07-29 | EMP-106 | PRJ-103 | 8 | Project
2026-07-30 | EMP-106 | PRJ-103 | 8 | Project
2026-07-31 | EMP-106 | PRJ-103 | 8 | Project
2026-08-03 | EMP-106 | PRJ-103 | 7.5 | Project
2026-08-04 | EMP-106 | PRJ-103 | 7.5 | Project
2026-08-05 | EMP-106 | PRJ-103 | 8 | Project
2026-08-06 | EMP-106 | PRJ-103 | 8 | Project
2026-08-07 | EMP-106 | PRJ-103 | 8 | Project
2026-06-29 | EMP-107 | PRJ-102 | 4 | Project
2026-06-29 | EMP-107 | PRJ-104 | 3 | Project
2026-06-30 | EMP-107 | PRJ-102 | 4 | Project
2026-06-30 | EMP-107 | PRJ-104 | 3 | Project
2026-07-01 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-01 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-02 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-02 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-03 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-03 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-06 | EMP-107 | PRJ-102 | 4 | Project
2026-07-06 | EMP-107 | PRJ-104 | 3 | Project
2026-07-07 | EMP-107 | PRJ-102 | 4 | Project
2026-07-07 | EMP-107 | PRJ-104 | 3 | Project
2026-07-08 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-08 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-09 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-09 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-10 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-10 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-14 | EMP-107 | PRJ-102 | 4 | Project
2026-07-14 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-15 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-15 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-16 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-16 | EMP-107 | PRJ-104 | 3 | Project
2026-07-17 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-17 | EMP-107 | PRJ-104 | 3 | Project
2026-07-20 | EMP-107 | PRJ-102 | 4 | Project
2026-07-20 | EMP-107 | PRJ-104 | 3 | Project
2026-07-21 | EMP-107 | PRJ-102 | 4 | Project
2026-07-21 | EMP-107 | PRJ-104 | 3 | Project
2026-07-22 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-22 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-23 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-23 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-24 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-24 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-27 | EMP-107 | PRJ-102 | 4 | Project
2026-07-27 | EMP-107 | PRJ-104 | 3 | Project
2026-07-28 | EMP-107 | PRJ-102 | 4 | Project
2026-07-28 | EMP-107 | PRJ-104 | 3 | Project
2026-07-29 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-29 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-30 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-30 | EMP-107 | PRJ-104 | 3.5 | Project
2026-07-31 | EMP-107 | PRJ-102 | 3.5 | Project
2026-07-31 | EMP-107 | PRJ-104 | 3.5 | Project
2026-08-03 | EMP-107 | PRJ-102 | 4 | Project
2026-08-03 | EMP-107 | PRJ-104 | 3 | Project
2026-08-04 | EMP-107 | PRJ-102 | 4 | Project
2026-08-04 | EMP-107 | PRJ-104 | 3 | Project
2026-08-05 | EMP-107 | PRJ-102 | 3.5 | Project
2026-08-05 | EMP-107 | PRJ-104 | 3.5 | Project
2026-08-06 | EMP-107 | PRJ-102 | 3.5 | Project
2026-08-06 | EMP-107 | PRJ-104 | 3.5 | Project
2026-08-07 | EMP-107 | PRJ-102 | 3.5 | Project
2026-08-07 | EMP-107 | PRJ-104 | 3.5 | Project
2026-06-29 | EMP-108 | PRJ-102 | 3.5 | Project
2026-06-29 | EMP-108 | PRJ-103 | 3 | Project
2026-06-30 | EMP-108 | PRJ-102 | 4 | Project
2026-06-30 | EMP-108 | PRJ-103 | 3 | Project
2026-07-01 | EMP-108 | PRJ-102 | 4 | Project
2026-07-01 | EMP-108 | PRJ-103 | 3 | Project
2026-07-02 | EMP-108 | PRJ-102 | 4 | Project
2026-07-02 | EMP-108 | PRJ-103 | 3 | Project
2026-07-03 | EMP-108 | PRJ-102 | 4 | Project
2026-07-03 | EMP-108 | PRJ-103 | 3 | Project
2026-07-06 | EMP-108 | PRJ-102 | 3.5 | Project
2026-07-06 | EMP-108 | PRJ-103 | 3 | Project
2026-07-07 | EMP-108 | PRJ-102 | 4 | Project
2026-07-07 | EMP-108 | PRJ-103 | 3 | Project
2026-07-08 | EMP-108 | PRJ-102 | 4 | Project
2026-07-08 | EMP-108 | PRJ-103 | 3 | Project
2026-07-09 | EMP-108 | PRJ-102 | 4 | Project
2026-07-09 | EMP-108 | PRJ-103 | 3 | Project
2026-07-10 | EMP-108 | PRJ-102 | 4 | Project
2026-07-10 | EMP-108 | PRJ-103 | 3 | Project
2026-07-14 | EMP-108 | PRJ-102 | 3.5 | Project
2026-07-14 | EMP-108 | PRJ-103 | 3 | Project
2026-07-15 | EMP-108 | PRJ-102 | 4 | Project
2026-07-15 | EMP-108 | PRJ-103 | 3 | Project
2026-07-16 | EMP-108 | PRJ-102 | 4 | Project
2026-07-16 | EMP-108 | PRJ-103 | 3 | Project
2026-07-17 | EMP-108 | PRJ-102 | 4 | Project
2026-07-17 | EMP-108 | PRJ-103 | 3 | Project
2026-07-20 | EMP-108 | PRJ-102 | 3.5 | Project
2026-07-20 | EMP-108 | PRJ-103 | 3 | Project
2026-07-21 | EMP-108 | PRJ-102 | 4 | Project
2026-07-21 | EMP-108 | PRJ-103 | 3 | Project
2026-07-22 | EMP-108 | PRJ-102 | 4 | Project
2026-07-22 | EMP-108 | PRJ-103 | 3 | Project
2026-07-23 | EMP-108 | PRJ-102 | 4 | Project
2026-07-23 | EMP-108 | PRJ-103 | 3 | Project
2026-07-24 | EMP-108 | PRJ-102 | 4 | Project
2026-07-24 | EMP-108 | PRJ-103 | 3 | Project
2026-07-27 | EMP-108 | PRJ-102 | 3.5 | Project
2026-07-27 | EMP-108 | PRJ-103 | 3 | Project
2026-07-28 | EMP-108 | PRJ-102 | 4 | Project
2026-07-28 | EMP-108 | PRJ-103 | 3 | Project
2026-07-29 | EMP-108 | PRJ-102 | 4 | Project
2026-07-29 | EMP-108 | PRJ-103 | 3 | Project
2026-07-30 | EMP-108 | PRJ-102 | 4 | Project
2026-07-30 | EMP-108 | PRJ-103 | 3 | Project
2026-07-31 | EMP-108 | PRJ-102 | 4 | Project
2026-07-31 | EMP-108 | PRJ-103 | 3 | Project
2026-08-03 | EMP-108 | PRJ-102 | 3.5 | Project
2026-08-03 | EMP-108 | PRJ-103 | 3 | Project
2026-08-04 | EMP-108 | PRJ-102 | 4 | Project
2026-08-04 | EMP-108 | PRJ-103 | 3 | Project
2026-08-05 | EMP-108 | PRJ-102 | 4 | Project
2026-08-05 | EMP-108 | PRJ-103 | 3 | Project
2026-08-06 | EMP-108 | PRJ-102 | 4 | Project
2026-08-06 | EMP-108 | PRJ-103 | 3 | Project
2026-08-07 | EMP-108 | PRJ-102 | 4 | Project
2026-08-07 | EMP-108 | PRJ-103 | 3 | Project
2026-06-29 | EMP-109 | PRJ-108 | 8.5 | Project
2026-06-30 | EMP-109 | PRJ-108 | 8 | Project
2026-07-01 | EMP-109 | PRJ-108 | 8 | Project
2026-07-02 | EMP-109 | PRJ-108 | 8 | Project
2026-07-03 | EMP-109 | PRJ-108 | 8 | Project
2026-07-06 | EMP-109 | PRJ-108 | 8.5 | Project
2026-07-07 | EMP-109 | PRJ-108 | 8 | Project
2026-07-08 | EMP-109 | PRJ-108 | 8 | Project
2026-07-09 | EMP-109 | PRJ-108 | 8 | Project
2026-07-10 | EMP-109 | PRJ-108 | 8 | Project
2026-07-14 | EMP-109 | PRJ-108 | 8 | Project
2026-07-15 | EMP-109 | PRJ-108 | 8 | Project
2026-07-16 | EMP-109 | PRJ-108 | 8 | Project
2026-07-17 | EMP-109 | PRJ-108 | 8 | Project
2026-07-20 | EMP-109 | PRJ-108 | 8.5 | Project
2026-07-21 | EMP-109 | PRJ-108 | 8 | Project
2026-07-22 | EMP-109 | PRJ-108 | 8 | Project
2026-07-23 | EMP-109 | PRJ-108 | 8 | Project
2026-07-24 | EMP-109 | PRJ-108 | 8 | Project
2026-07-27 | EMP-109 | PRJ-108 | 8.5 | Project
2026-07-28 | EMP-109 | PRJ-108 | 8 | Project
2026-07-29 | EMP-109 | PRJ-108 | 8 | Project
2026-07-30 | EMP-109 | PRJ-108 | 8 | Project
2026-07-31 | EMP-109 | PRJ-108 | 8 | Project
2026-08-03 | EMP-109 | PRJ-108 | 8.5 | Project
2026-08-04 | EMP-109 | PRJ-108 | 8 | Project
2026-08-05 | EMP-109 | PRJ-108 | 8 | Project
2026-08-06 | EMP-109 | PRJ-108 | 8 | Project
2026-08-07 | EMP-109 | PRJ-108 | 8 | Project
2026-06-29 | EMP-110 | PRJ-101 | 4.5 | Project
2026-06-29 | EMP-110 | PRJ-105 | 3 | Project
2026-06-30 | EMP-110 | PRJ-101 | 4.5 | Project
2026-06-30 | EMP-110 | PRJ-105 | 3 | Project
2026-07-01 | EMP-110 | PRJ-101 | 4 | Project
2026-07-01 | EMP-110 | PRJ-105 | 3 | Project
2026-07-02 | EMP-110 | PRJ-101 | 4 | Project
2026-07-02 | EMP-110 | PRJ-105 | 3 | Project
2026-07-03 | EMP-110 | PRJ-101 | 4 | Project
2026-07-03 | EMP-110 | PRJ-105 | 3 | Project
2026-07-06 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-06 | EMP-110 | PRJ-105 | 3 | Project
2026-07-07 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-07 | EMP-110 | PRJ-105 | 3 | Project
2026-07-08 | EMP-110 | PRJ-101 | 4 | Project
2026-07-08 | EMP-110 | PRJ-105 | 3 | Project
2026-07-09 | EMP-110 | PRJ-101 | 4 | Project
2026-07-09 | EMP-110 | PRJ-105 | 3 | Project
2026-07-10 | EMP-110 | PRJ-101 | 4 | Project
2026-07-10 | EMP-110 | PRJ-105 | 3 | Project
2026-07-14 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-14 | EMP-110 | PRJ-105 | 3 | Project
2026-07-15 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-15 | EMP-110 | PRJ-105 | 3 | Project
2026-07-16 | EMP-110 | PRJ-101 | 4 | Project
2026-07-16 | EMP-110 | PRJ-105 | 3 | Project
2026-07-17 | EMP-110 | PRJ-101 | 4 | Project
2026-07-17 | EMP-110 | PRJ-105 | 3 | Project
2026-07-20 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-20 | EMP-110 | PRJ-105 | 3 | Project
2026-07-21 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-21 | EMP-110 | PRJ-105 | 3 | Project
2026-07-22 | EMP-110 | PRJ-101 | 4 | Project
2026-07-22 | EMP-110 | PRJ-105 | 3 | Project
2026-07-23 | EMP-110 | PRJ-101 | 4 | Project
2026-07-23 | EMP-110 | PRJ-105 | 3 | Project
2026-07-24 | EMP-110 | PRJ-101 | 4 | Project
2026-07-24 | EMP-110 | PRJ-105 | 3 | Project
2026-07-27 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-27 | EMP-110 | PRJ-105 | 3 | Project
2026-07-28 | EMP-110 | PRJ-101 | 4.5 | Project
2026-07-28 | EMP-110 | PRJ-105 | 3 | Project
2026-07-29 | EMP-110 | PRJ-101 | 4 | Project
2026-07-29 | EMP-110 | PRJ-105 | 3 | Project
2026-07-30 | EMP-110 | PRJ-101 | 4 | Project
2026-07-30 | EMP-110 | PRJ-105 | 3 | Project
2026-07-31 | EMP-110 | PRJ-101 | 4 | Project
2026-07-31 | EMP-110 | PRJ-105 | 3 | Project
2026-08-03 | EMP-110 | PRJ-101 | 4.5 | Project
2026-08-03 | EMP-110 | PRJ-105 | 3 | Project
2026-08-04 | EMP-110 | PRJ-101 | 4.5 | Project
2026-08-04 | EMP-110 | PRJ-105 | 3 | Project
2026-08-05 | EMP-110 | PRJ-101 | 4 | Project
2026-08-05 | EMP-110 | PRJ-105 | 3 | Project
2026-08-06 | EMP-110 | PRJ-101 | 4 | Project
2026-08-06 | EMP-110 | PRJ-105 | 3 | Project
2026-08-07 | EMP-110 | PRJ-101 | 4 | Project
2026-08-07 | EMP-110 | PRJ-105 | 3 | Project
2026-06-29 | EMP-111 | PRJ-105 | 8 | Project
2026-06-30 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-01 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-02 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-03 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-06 | EMP-111 | PRJ-105 | 8 | Project
2026-07-07 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-08 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-09 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-10 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-14 | EMP-111 | PRJ-105 | 8 | Project
2026-07-15 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-16 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-17 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-20 | EMP-111 | PRJ-105 | 8 | Project
2026-07-21 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-22 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-23 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-24 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-27 | EMP-111 | PRJ-105 | 8 | Project
2026-07-28 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-29 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-30 | EMP-111 | PRJ-105 | 7.5 | Project
2026-07-31 | EMP-111 | PRJ-105 | 7.5 | Project
2026-08-03 | EMP-111 | PRJ-105 | 8 | Project
2026-08-04 | EMP-111 | PRJ-105 | 7.5 | Project
2026-08-05 | EMP-111 | PRJ-105 | 7.5 | Project
2026-08-06 | EMP-111 | PRJ-105 | 7.5 | Project
2026-08-07 | EMP-111 | PRJ-105 | 7.5 | Project
2026-06-29 | EMP-112 | PRJ-102 | 5 | Project
2026-06-29 | EMP-112 | PRJ-105 | 4 | Project
2026-06-30 | EMP-112 | PRJ-102 | 5 | Project
2026-06-30 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-01 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-01 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-02 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-02 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-03 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-03 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-06 | EMP-112 | PRJ-102 | 5 | Project
2026-07-06 | EMP-112 | PRJ-105 | 4 | Project
2026-07-07 | EMP-112 | PRJ-102 | 5 | Project
2026-07-07 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-08 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-08 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-09 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-09 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-10 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-10 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-14 | EMP-112 | PRJ-102 | 5 | Project
2026-07-14 | EMP-112 | PRJ-105 | 4 | Project
2026-07-15 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-15 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-16 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-16 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-17 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-17 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-20 | EMP-112 | PRJ-102 | 5 | Project
2026-07-20 | EMP-112 | PRJ-105 | 4 | Project
2026-07-21 | EMP-112 | PRJ-102 | 5 | Project
2026-07-21 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-22 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-22 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-23 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-23 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-24 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-24 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-27 | EMP-112 | PRJ-102 | 5 | Project
2026-07-27 | EMP-112 | PRJ-105 | 4 | Project
2026-07-28 | EMP-112 | PRJ-102 | 5 | Project
2026-07-28 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-29 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-29 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-30 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-30 | EMP-112 | PRJ-105 | 3.5 | Project
2026-07-31 | EMP-112 | PRJ-102 | 4.5 | Project
2026-07-31 | EMP-112 | PRJ-105 | 3.5 | Project
2026-08-03 | EMP-112 | PRJ-102 | 5 | Project
2026-08-03 | EMP-112 | PRJ-105 | 4 | Project
2026-08-04 | EMP-112 | PRJ-102 | 5 | Project
2026-08-04 | EMP-112 | PRJ-105 | 3.5 | Project
2026-08-05 | EMP-112 | PRJ-102 | 4.5 | Project
2026-08-05 | EMP-112 | PRJ-105 | 3.5 | Project
2026-08-06 | EMP-112 | PRJ-102 | 4.5 | Project
2026-08-06 | EMP-112 | PRJ-105 | 3.5 | Project
2026-08-07 | EMP-112 | PRJ-102 | 4.5 | Project
2026-08-07 | EMP-112 | PRJ-105 | 3.5 | Project
2026-06-29 | EMP-113 | PRJ-106 | 3 | Project
2026-06-30 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-01 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-02 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-03 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-06 | EMP-113 | PRJ-106 | 3 | Project
2026-07-07 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-08 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-09 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-10 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-14 | EMP-113 | PRJ-106 | 3 | Project
2026-07-15 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-16 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-17 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-20 | EMP-113 | PRJ-106 | 3 | Project
2026-07-21 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-22 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-23 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-24 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-27 | EMP-113 | PRJ-106 | 3 | Project
2026-07-28 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-29 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-30 | EMP-113 | PRJ-106 | 3.5 | Project
2026-07-31 | EMP-113 | PRJ-106 | 3.5 | Project
2026-08-03 | EMP-113 | PRJ-106 | 3 | Project
2026-08-04 | EMP-113 | PRJ-106 | 3.5 | Project
2026-08-05 | EMP-113 | PRJ-106 | 3.5 | Project
2026-08-06 | EMP-113 | PRJ-106 | 3.5 | Project
2026-08-07 | EMP-113 | PRJ-106 | 3.5 | Project
2026-06-29 | EMP-114 | PRJ-102 | 2 | Project
2026-06-29 | EMP-114 | PRJ-108 | 1.5 | Project
2026-06-30 | EMP-114 | PRJ-102 | 2 | Project
2026-06-30 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-01 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-01 | EMP-114 | PRJ-108 | 2 | Project
2026-07-02 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-02 | EMP-114 | PRJ-108 | 2 | Project
2026-07-03 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-03 | EMP-114 | PRJ-108 | 2 | Project
2026-07-06 | EMP-114 | PRJ-102 | 2 | Project
2026-07-06 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-07 | EMP-114 | PRJ-102 | 2 | Project
2026-07-07 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-08 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-08 | EMP-114 | PRJ-108 | 2 | Project
2026-07-09 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-09 | EMP-114 | PRJ-108 | 2 | Project
2026-07-10 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-10 | EMP-114 | PRJ-108 | 2 | Project
2026-07-14 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-14 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-15 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-15 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-16 | EMP-114 | PRJ-102 | 2 | Project
2026-07-16 | EMP-114 | PRJ-108 | 2 | Project
2026-07-17 | EMP-114 | PRJ-102 | 2 | Project
2026-07-17 | EMP-114 | PRJ-108 | 2 | Project
2026-07-20 | EMP-114 | PRJ-102 | 2 | Project
2026-07-20 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-21 | EMP-114 | PRJ-102 | 2 | Project
2026-07-21 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-22 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-22 | EMP-114 | PRJ-108 | 2 | Project
2026-07-23 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-23 | EMP-114 | PRJ-108 | 2 | Project
2026-07-24 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-24 | EMP-114 | PRJ-108 | 2 | Project
2026-07-27 | EMP-114 | PRJ-102 | 2 | Project
2026-07-27 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-28 | EMP-114 | PRJ-102 | 2 | Project
2026-07-28 | EMP-114 | PRJ-108 | 1.5 | Project
2026-07-29 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-29 | EMP-114 | PRJ-108 | 2 | Project
2026-07-30 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-30 | EMP-114 | PRJ-108 | 2 | Project
2026-07-31 | EMP-114 | PRJ-102 | 1.5 | Project
2026-07-31 | EMP-114 | PRJ-108 | 2 | Project
2026-08-03 | EMP-114 | PRJ-102 | 2 | Project
2026-08-03 | EMP-114 | PRJ-108 | 1.5 | Project
2026-08-04 | EMP-114 | PRJ-102 | 2 | Project
2026-08-04 | EMP-114 | PRJ-108 | 1.5 | Project
2026-08-05 | EMP-114 | PRJ-102 | 1.5 | Project
2026-08-05 | EMP-114 | PRJ-108 | 2 | Project
2026-08-06 | EMP-114 | PRJ-102 | 1.5 | Project
2026-08-06 | EMP-114 | PRJ-108 | 2 | Project
2026-08-07 | EMP-114 | PRJ-102 | 1.5 | Project
2026-08-07 | EMP-114 | PRJ-108 | 2 | Project
2026-06-29 | EMP-115 | PRJ-102 | 5 | Project
2026-06-29 | EMP-115 | PRJ-105 | 2.5 | Project
2026-06-30 | EMP-115 | PRJ-102 | 5 | Project
2026-06-30 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-01 | EMP-115 | PRJ-102 | 5 | Project
2026-07-01 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-02 | EMP-115 | PRJ-102 | 5 | Project
2026-07-02 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-03 | EMP-115 | PRJ-102 | 5 | Project
2026-07-03 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-06 | EMP-115 | PRJ-102 | 5 | Project
2026-07-06 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-07 | EMP-115 | PRJ-102 | 5 | Project
2026-07-07 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-08 | EMP-115 | PRJ-102 | 5 | Project
2026-07-08 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-09 | EMP-115 | PRJ-102 | 5 | Project
2026-07-09 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-10 | EMP-115 | PRJ-102 | 5 | Project
2026-07-10 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-14 | EMP-115 | PRJ-102 | 5 | Project
2026-07-14 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-15 | EMP-115 | PRJ-102 | 5 | Project
2026-07-15 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-16 | EMP-115 | PRJ-102 | 5 | Project
2026-07-16 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-17 | EMP-115 | PRJ-102 | 5 | Project
2026-07-17 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-20 | EMP-115 | PRJ-102 | 5 | Project
2026-07-20 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-21 | EMP-115 | PRJ-102 | 5 | Project
2026-07-21 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-22 | EMP-115 | PRJ-102 | 5 | Project
2026-07-22 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-23 | EMP-115 | PRJ-102 | 5 | Project
2026-07-23 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-24 | EMP-115 | PRJ-102 | 5 | Project
2026-07-24 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-27 | EMP-115 | PRJ-102 | 5 | Project
2026-07-27 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-28 | EMP-115 | PRJ-102 | 5 | Project
2026-07-28 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-29 | EMP-115 | PRJ-102 | 5 | Project
2026-07-29 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-30 | EMP-115 | PRJ-102 | 5 | Project
2026-07-30 | EMP-115 | PRJ-105 | 2.5 | Project
2026-07-31 | EMP-115 | PRJ-102 | 5 | Project
2026-07-31 | EMP-115 | PRJ-105 | 2.5 | Project
2026-08-03 | EMP-115 | PRJ-102 | 5 | Project
2026-08-03 | EMP-115 | PRJ-105 | 2.5 | Project
2026-08-04 | EMP-115 | PRJ-102 | 5 | Project
2026-08-04 | EMP-115 | PRJ-105 | 2.5 | Project
2026-08-05 | EMP-115 | PRJ-102 | 5 | Project
2026-08-05 | EMP-115 | PRJ-105 | 2.5 | Project
2026-08-06 | EMP-115 | PRJ-102 | 5 | Project
2026-08-06 | EMP-115 | PRJ-105 | 2.5 | Project
2026-08-07 | EMP-115 | PRJ-102 | 5 | Project
2026-08-07 | EMP-115 | PRJ-105 | 2.5 | Project
2026-06-29 | EMP-116 | PRJ-104 | 4 | Project
2026-06-29 | EMP-116 | PRJ-105 | 3.5 | Project
2026-06-30 | EMP-116 | PRJ-104 | 4 | Project
2026-06-30 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-01 | EMP-116 | PRJ-104 | 4 | Project
2026-07-01 | EMP-116 | PRJ-105 | 4 | Project
2026-07-02 | EMP-116 | PRJ-104 | 4 | Project
2026-07-02 | EMP-116 | PRJ-105 | 4 | Project
2026-07-03 | EMP-116 | PRJ-104 | 4 | Project
2026-07-03 | EMP-116 | PRJ-105 | 4 | Project
2026-07-06 | EMP-116 | PRJ-104 | 4 | Project
2026-07-06 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-07 | EMP-116 | PRJ-104 | 4 | Project
2026-07-07 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-08 | EMP-116 | PRJ-104 | 4 | Project
2026-07-08 | EMP-116 | PRJ-105 | 4 | Project
2026-07-09 | EMP-116 | PRJ-104 | 4 | Project
2026-07-09 | EMP-116 | PRJ-105 | 4 | Project
2026-07-10 | EMP-116 | PRJ-104 | 4 | Project
2026-07-10 | EMP-116 | PRJ-105 | 4 | Project
2026-07-14 | EMP-116 | PRJ-104 | 4 | Project
2026-07-14 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-15 | EMP-116 | PRJ-104 | 4 | Project
2026-07-15 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-16 | EMP-116 | PRJ-104 | 4 | Project
2026-07-16 | EMP-116 | PRJ-105 | 4 | Project
2026-07-17 | EMP-116 | PRJ-104 | 4 | Project
2026-07-17 | EMP-116 | PRJ-105 | 4 | Project
2026-07-20 | EMP-116 | PRJ-104 | 4 | Project
2026-07-20 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-21 | EMP-116 | PRJ-104 | 4 | Project
2026-07-21 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-22 | EMP-116 | PRJ-104 | 4 | Project
2026-07-22 | EMP-116 | PRJ-105 | 4 | Project
2026-07-23 | EMP-116 | PRJ-104 | 4 | Project
2026-07-23 | EMP-116 | PRJ-105 | 4 | Project
2026-07-24 | EMP-116 | PRJ-104 | 4 | Project
2026-07-24 | EMP-116 | PRJ-105 | 4 | Project
2026-07-27 | EMP-116 | PRJ-104 | 4 | Project
2026-07-27 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-28 | EMP-116 | PRJ-104 | 4 | Project
2026-07-28 | EMP-116 | PRJ-105 | 3.5 | Project
2026-07-29 | EMP-116 | PRJ-104 | 4 | Project
2026-07-29 | EMP-116 | PRJ-105 | 4 | Project
2026-07-30 | EMP-116 | PRJ-104 | 4 | Project
2026-07-30 | EMP-116 | PRJ-105 | 4 | Project
2026-07-31 | EMP-116 | PRJ-104 | 4 | Project
2026-07-31 | EMP-116 | PRJ-105 | 4 | Project
2026-08-03 | EMP-116 | PRJ-104 | 4 | Project
2026-08-03 | EMP-116 | PRJ-105 | 3.5 | Project
2026-08-04 | EMP-116 | PRJ-104 | 4 | Project
2026-08-04 | EMP-116 | PRJ-105 | 3.5 | Project
2026-08-05 | EMP-116 | PRJ-104 | 4 | Project
2026-08-05 | EMP-116 | PRJ-105 | 4 | Project
2026-08-06 | EMP-116 | PRJ-104 | 4 | Project
2026-08-06 | EMP-116 | PRJ-105 | 4 | Project
2026-08-07 | EMP-116 | PRJ-104 | 4 | Project
2026-08-07 | EMP-116 | PRJ-105 | 4 | Project
2026-06-29 | EMP-117 | PRJ-102 | 3.5 | Project
2026-06-29 | EMP-117 | PRJ-106 | 4.5 | Project
2026-06-30 | EMP-117 | PRJ-102 | 4 | Project
2026-06-30 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-01 | EMP-117 | PRJ-102 | 4 | Project
2026-07-01 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-02 | EMP-117 | PRJ-102 | 4 | Project
2026-07-02 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-03 | EMP-117 | PRJ-102 | 4 | Project
2026-07-03 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-06 | EMP-117 | PRJ-102 | 3.5 | Project
2026-07-06 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-07 | EMP-117 | PRJ-102 | 4 | Project
2026-07-07 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-08 | EMP-117 | PRJ-102 | 4 | Project
2026-07-08 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-09 | EMP-117 | PRJ-102 | 4 | Project
2026-07-09 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-10 | EMP-117 | PRJ-102 | 4 | Project
2026-07-10 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-14 | EMP-117 | PRJ-102 | 3.5 | Project
2026-07-14 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-15 | EMP-117 | PRJ-102 | 4 | Project
2026-07-15 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-16 | EMP-117 | PRJ-102 | 4 | Project
2026-07-16 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-17 | EMP-117 | PRJ-102 | 4 | Project
2026-07-17 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-20 | EMP-117 | PRJ-102 | 3.5 | Project
2026-07-20 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-21 | EMP-117 | PRJ-102 | 4 | Project
2026-07-21 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-22 | EMP-117 | PRJ-102 | 4 | Project
2026-07-22 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-23 | EMP-117 | PRJ-102 | 4 | Project
2026-07-23 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-24 | EMP-117 | PRJ-102 | 4 | Project
2026-07-24 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-27 | EMP-117 | PRJ-102 | 3.5 | Project
2026-07-27 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-28 | EMP-117 | PRJ-102 | 4 | Project
2026-07-28 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-29 | EMP-117 | PRJ-102 | 4 | Project
2026-07-29 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-30 | EMP-117 | PRJ-102 | 4 | Project
2026-07-30 | EMP-117 | PRJ-106 | 4.5 | Project
2026-07-31 | EMP-117 | PRJ-102 | 4 | Project
2026-07-31 | EMP-117 | PRJ-106 | 4.5 | Project
2026-08-03 | EMP-117 | PRJ-102 | 3.5 | Project
2026-08-03 | EMP-117 | PRJ-106 | 4.5 | Project
2026-08-04 | EMP-117 | PRJ-102 | 4 | Project
2026-08-04 | EMP-117 | PRJ-106 | 4.5 | Project
2026-08-05 | EMP-117 | PRJ-102 | 4 | Project
2026-08-05 | EMP-117 | PRJ-106 | 4.5 | Project
2026-08-06 | EMP-117 | PRJ-102 | 4 | Project
2026-08-06 | EMP-117 | PRJ-106 | 4.5 | Project
2026-08-07 | EMP-117 | PRJ-102 | 4 | Project
2026-08-07 | EMP-117 | PRJ-106 | 4.5 | Project
2026-06-29 | EMP-118 | PRJ-101 | 3.5 | Project
2026-06-29 | EMP-118 | PRJ-105 | 5 | Project
2026-06-30 | EMP-118 | PRJ-101 | 3.5 | Project
2026-06-30 | EMP-118 | PRJ-105 | 5 | Project
2026-07-01 | EMP-118 | PRJ-101 | 4 | Project
2026-07-01 | EMP-118 | PRJ-105 | 5 | Project
2026-07-02 | EMP-118 | PRJ-101 | 4 | Project
2026-07-02 | EMP-118 | PRJ-105 | 5 | Project
2026-07-03 | EMP-118 | PRJ-101 | 4 | Project
2026-07-03 | EMP-118 | PRJ-105 | 5 | Project
2026-07-06 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-06 | EMP-118 | PRJ-105 | 5 | Project
2026-07-07 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-07 | EMP-118 | PRJ-105 | 5 | Project
2026-07-08 | EMP-118 | PRJ-101 | 4 | Project
2026-07-08 | EMP-118 | PRJ-105 | 5 | Project
2026-07-09 | EMP-118 | PRJ-101 | 4 | Project
2026-07-09 | EMP-118 | PRJ-105 | 5 | Project
2026-07-10 | EMP-118 | PRJ-101 | 4 | Project
2026-07-10 | EMP-118 | PRJ-105 | 5 | Project
2026-07-14 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-14 | EMP-118 | PRJ-105 | 5 | Project
2026-07-15 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-15 | EMP-118 | PRJ-105 | 5 | Project
2026-07-16 | EMP-118 | PRJ-101 | 4 | Project
2026-07-16 | EMP-118 | PRJ-105 | 5 | Project
2026-07-17 | EMP-118 | PRJ-101 | 4 | Project
2026-07-17 | EMP-118 | PRJ-105 | 5 | Project
2026-07-20 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-20 | EMP-118 | PRJ-105 | 5 | Project
2026-07-21 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-21 | EMP-118 | PRJ-105 | 5 | Project
2026-07-22 | EMP-118 | PRJ-101 | 4 | Project
2026-07-22 | EMP-118 | PRJ-105 | 5 | Project
2026-07-23 | EMP-118 | PRJ-101 | 4 | Project
2026-07-23 | EMP-118 | PRJ-105 | 5 | Project
2026-07-24 | EMP-118 | PRJ-101 | 4 | Project
2026-07-24 | EMP-118 | PRJ-105 | 5 | Project
2026-07-27 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-27 | EMP-118 | PRJ-105 | 5 | Project
2026-07-28 | EMP-118 | PRJ-101 | 3.5 | Project
2026-07-28 | EMP-118 | PRJ-105 | 5 | Project
2026-07-29 | EMP-118 | PRJ-101 | 4 | Project
2026-07-29 | EMP-118 | PRJ-105 | 5 | Project
2026-07-30 | EMP-118 | PRJ-101 | 4 | Project
2026-07-30 | EMP-118 | PRJ-105 | 5 | Project
2026-07-31 | EMP-118 | PRJ-101 | 4 | Project
2026-07-31 | EMP-118 | PRJ-105 | 5 | Project
2026-08-03 | EMP-118 | PRJ-101 | 3.5 | Project
2026-08-03 | EMP-118 | PRJ-105 | 5 | Project
2026-08-04 | EMP-118 | PRJ-101 | 3.5 | Project
2026-08-04 | EMP-118 | PRJ-105 | 5 | Project
2026-08-05 | EMP-118 | PRJ-101 | 4 | Project
2026-08-05 | EMP-118 | PRJ-105 | 5 | Project
2026-08-06 | EMP-118 | PRJ-101 | 4 | Project
2026-08-06 | EMP-118 | PRJ-105 | 5 | Project
2026-08-07 | EMP-118 | PRJ-101 | 4 | Project
2026-08-07 | EMP-118 | PRJ-105 | 5 | Project

## DS04_Leave_Holiday_Records
leave_date | member_id | LEAVE_TYPE | approved | duration_days | record_id | note
2026-07-13 |  | Public Holiday | TRUE | 1 | LV-0001 | Company-wide holiday
2026-07-06 | EMP-003 | Annual Leave | TRUE | 1 | LV-0002 | Approved annual leave (full week)
2026-07-07 | EMP-003 | Annual Leave | TRUE | 1 | LV-0003 | Approved annual leave (full week)
2026-07-08 | EMP-003 | Annual Leave | TRUE | 1 | LV-0004 | Approved annual leave (full week)
2026-07-09 | EMP-003 | Annual Leave | TRUE | 1 | LV-0005 | Approved annual leave (full week)
2026-07-10 | EMP-003 | Annual Leave | TRUE | 1 | LV-0006 | Approved annual leave (full week)
2026-07-27 | EMP-003 | Approved OT Comp | TRUE | 1 | LV-0007 | Approved OT — exclude from over-log flag
2026-07-28 | EMP-003 | Approved OT Comp | TRUE | 1 | LV-0008 | Approved OT — exclude from over-log flag
2026-07-14 | EMP-009 | Training | TRUE | 1 | LV-0009 | Onboarding training (also logged in timesheet)
2026-07-15 | EMP-009 | Training | TRUE | 1 | LV-0010 | Onboarding training (also logged in timesheet)
2026-07-16 | EMP-009 | Training | TRUE | 1 | LV-0011 | Onboarding training (also logged in timesheet)

## DS05_Project_Master
Shared master — identical rows appear in PMO_01 file.
project_name | PROJECT_ID | project_type | account_id | Status | PM_ID | Start_date | End_date
Project Orion (Core Banking) | PRJ-001 | Software/Migration | ACC-A | Active | EMP-012 | 2026-05-19 | 2026-12-19
Energent AI (Data Platform) | PRJ-002 | AI/ML Platform | ACC-B | Active | EMP-012 | 2026-04-06 | 2026-12-31
Project Titan (Internal Tools) | PRJ-003 | Software | ACC-A | Active | EMP-011 | 2026-06-01 | 2026-10-31
Mercury Core Migration | PRJ-H-101 | Software/Migration | ACC-A | Completed | EMP-012 | 2025-01-06 | 2025-09-05
Saturn Banking Upgrade | PRJ-H-102 | Software/Migration | ACC-A | Completed | EMP-012 | 2025-02-03 | 2025-09-01
Comet ML Pipeline | PRJ-H-103 | AI/ML Platform | ACC-B | Completed | EMP-011 | 2024-10-07 | 2025-07-07
Nebula Forecast Engine | PRJ-H-104 | AI/ML Platform | ACC-B | Completed | EMP-011 | 2024-11-04 | 2025-07-21
Pulsar CRM | PRJ-H-105 | Software | ACC-C | Completed | EMP-012 | 2025-03-03 | 2025-07-01
Flux POC | PRJ-H-199 | AI/ML Platform | ACC-C | Completed | EMP-011 | 2025-05-01 | 2025-05-16
Project Apollo | PRJ-101 | Software/Migration | ACC-E | Active | EMP-012 | 2026-04-05 | 2026-09-12
Project Vega | PRJ-102 | Software | ACC-C | Active | EMP-101 | 2026-04-11 | 2026-11-11
Project Lyra | PRJ-103 | Software/Migration | ACC-C | Active | EMP-012 | 2026-03-08 | 2026-10-16
Project Draco | PRJ-104 | Integration | ACC-B | Active | EMP-101 | 2026-04-27 | 2026-12-06
Project Orbit | PRJ-105 | Integration | ACC-D | Active | EMP-101 | 2026-06-21 | 2026-11-05
Project Helios | PRJ-106 | Software/Migration | ACC-A | Active | EMP-102 | 2026-03-28 | 2026-10-26
Project Atlas | PRJ-107 | Mobile | ACC-A | Active | EMP-012 | 2026-03-23 | 2026-10-09
Project Zephyr | PRJ-108 | Data | ACC-A | Active | EMP-102 | 2026-06-07 | 2026-11-08
Project Zephyr (archived) | PRJ-H-201 | Software/Migration | ACC-E | Completed | EMP-012 | 2024-04-28 | 2025-02-15
Project Cobalt (archived) | PRJ-H-202 | Software/Migration | ACC-C | Completed | EMP-011 | 2024-04-27 | 2025-01-15
Project Quartz (archived) | PRJ-H-203 | Software | ACC-C | Completed | EMP-102 | 2024-08-24 | 2025-09-16
Project Nimbus (archived) | PRJ-H-204 | Data | ACC-B | Completed | EMP-011 | 2024-03-12 | 2025-03-02
Project Cedar (archived) | PRJ-H-205 | Software | ACC-D | Completed | EMP-012 | 2024-04-04 | 2025-07-04
Project Falcon (archived) | PRJ-H-206 | Integration | ACC-A | Completed | EMP-101 | 2024-07-05 | 2025-08-07

## DS06_Member_Master
Shared master — identical rows appear in PMO_01 file.
full_name | MEMBER_ID | role_title | department | Level | employment | std_hours_week | join_date | Line_manager_id | Employment_status
Nguyen Van An | EMP-001 | Backend Developer | Backend | L3 | FT | 40 | 2023-03-01 | EMP-004 | Active
Tran Thi Bich | EMP-002 | Data Engineer | Data | L3 | FT | 40 | 2022-09-12 | EMP-011 | Active
Le Van Cuong | EMP-003 | ML Engineer | AI/ML | L4 | FT | 40 | 2021-06-01 | EMP-011 | Active
Pham Thi Dung | EMP-004 | Backend Lead | Backend | L5 | FT | 40 | 2019-02-18 | EMP-011 | Active
Hoang Van Em | EMP-005 | DevOps Engineer | Platform | L4 | FT | 40 | 2022-01-10 | EMP-011 | Active
Do Van Khoa | EMP-006 | Security Engineer | Security | L4 | FT | 40 | 2020-11-03 | EMP-011 | Active
Bui Thi Hoa | EMP-007 | UX/UI Designer | Design | L3 | PT | 20 | 2023-08-21 | EMP-012 | Active
Ngo Thi Lan | EMP-008 | Business Analyst | BA | L3 | FT | 40 | 2022-04-04 | EMP-012 | Active
Ly Van Minh | EMP-009 | Frontend Developer | Frontend | L2 | FT | 40 | 2026-07-14 | EMP-004 | Probation
Truong Thi Nga | EMP-010 | QA Engineer | QA | L3 | FT | 40 | 2021-10-07 | EMP-004 | Active
Vu Thi Mai | EMP-011 | Engineering Manager | Engineering | L6 | FT | 40 | 2017-05-02 | EMP-012 | Active
Dang Van Phuc | EMP-012 | PMO Lead / PM | PMO | L6 | FT | 40 | 2016-01-15 |  | Active
Le Anh Tuan | EMP-101 | Project Manager | PMO | L5 | FT | 40 | 2019-09-28 | EMP-101 | Active
Dao Chi Nam | EMP-102 | Project Manager | PMO | L5 | FT | 40 | 2019-07-23 | EMP-011 | Active
Hoang Hieu Nam | EMP-103 | Backend Developer | Backend | L3 | FT | 40 | 2020-11-01 | EMP-011 | Active
Do My Quan | EMP-104 | Business Analyst | BA | L4 | FT | 40 | 2024-08-06 | EMP-101 | Active
Do Trang Binh | EMP-105 | DevOps Engineer | Platform | L2 | FT | 40 | 2020-03-11 | EMP-101 | Active
Do Yen Quynh | EMP-106 | Frontend Developer | Frontend | L5 | FT | 40 | 2024-12-06 | EMP-101 | Active
Ho Hung Thao | EMP-107 | Data Engineer | Data | L3 | FT | 40 | 2023-07-06 | EMP-101 | Active
Phan Nhung My | EMP-108 | Frontend Developer | Frontend | L3 | FT | 40 | 2020-10-28 | EMP-011 | Active
Phan Ha Ha | EMP-109 | DevOps Engineer | Platform | L5 | FT | 40 | 2023-01-21 | EMP-011 | Active
Pham Trang Anh | EMP-110 | Frontend Developer | Frontend | L4 | FT | 40 | 2021-05-11 | EMP-011 | Active
Do Anh Hieu | EMP-111 | Business Analyst | BA | L4 | FT | 40 | 2020-02-03 | EMP-102 | Active
Ngo Tuan Hieu | EMP-112 | Business Analyst | BA | L3 | FT | 40 | 2024-01-11 | EMP-012 | Active
Pham Ha Viet | EMP-113 | Backend Developer | Backend | L2 | PT | 20 | 2018-11-15 | EMP-101 | Active
Tran Long Giang | EMP-114 | UX/UI Designer | Design | L5 | PT | 20 | 2023-02-04 | EMP-012 | Active
Cao Nam Long | EMP-115 | UX/UI Designer | Design | L5 | FT | 40 | 2020-02-19 | EMP-011 | Active
Cao Ngan Thao | EMP-116 | QA Engineer | QA | L4 | FT | 40 | 2024-06-01 | EMP-012 | Active
Duong Dat Chi | EMP-117 | ML Engineer | AI/ML | L4 | FT | 40 | 2021-01-08 | EMP-101 | Active
Duong Nhung Binh | EMP-118 | UX/UI Designer | Design | L3 | FT | 40 | 2024-01-19 | EMP-101 | Active

## Answer_Key
Case_ID | 08_schema_tolerance
Description | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows.
Finding_ID | Entity_type | Entity_id | Issue_type | Week_ID | Expected_detection | Severity
08_schema_tolerance-F01 | Member | EMP-004 | overbook |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | High
08_schema_tolerance-F02 | Member | EMP-001 | overbook |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Medium
08_schema_tolerance-F03 | Member | EMP-005 | idle |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Medium
08_schema_tolerance-F04 | Member | EMP-008 | idle |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Medium
08_schema_tolerance-F05 | Member | EMP-002 | mismatch_under |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Medium
08_schema_tolerance-F06 | Member | EMP-006 | mismatch_over |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | High
08_schema_tolerance-F07 | Member | EMP-003 | edge_exclude | W2 | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Info
08_schema_tolerance-F08 | Week | W3 | edge_holiday | W3 | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Info
08_schema_tolerance-F09 | Member | EMP-009 | edge_onboard_missing | W1 | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Info
08_schema_tolerance-F10 | Member | EMP-010 | data_duplicate |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | High
08_schema_tolerance-F11 | Member | EMP-007 | guardrail_parttime |  | Shuffles selected columns and changes header case/whitespace while preserving sheet names and header rows. | Info
Recommendation_ID | Source_member_id | Week_ID | Expected_status | Expected_top_targets
Data_quality_degraded | false
Required_flags
Eval_prompts
Ingest 08_schema_tolerance, normalize PMO tables, and summarize required data-quality review gates.
Generate an overbook/idle/mismatch report for 2026-06-29 to 2026-08-07.
Recommend rebalance options for the highest-risk overbooked member in 08_schema_tolerance.