## LEGEND & SUMMARY
PMO 02 - Resource Allocation & Timesheet Monitoring Agent ¦ Mock Dataset
Input for an agent that standardizes RA + Timesheet into a member-project-week view, flags overbook/idle, compares planned RA% vs actual logged hours, and excludes valid edge cases (leave/holiday/training/approved OT). Shared masters (members, projects) are identical to the PMO 01 file. Watch for one DUPLICATED RA row (do not double-count) and members with missing weeks (onboarding).
Sheet | Grain (1 row =) | Field | Type | Example | Description
DS01_Resource_Allocation | 1 member x project allocation (the plan) | Member_ID | String | EMP-004 | Member (FK -> Member_Master).
|  | Project_ID | String | PRJ-002 | Project (FK -> Project_Master).
|  | Role | Enum | BE | Role code on this allocation.
|  | Allocation_pct | Float | 0.45 | Planned RA% (share of standard week).
|  | Start_date | Date | 2026-06-29 | Allocation start.
|  | End_date | Date | 2026-08-07 | Allocation end.
|  | Weekly_planned_hours | Float | 18.0 | allocation_pct x member's std week (PT-aware!).
DS02_Timesheet_Log | 1 member x day x project log | Member_ID | String | EMP-004 | Member (FK).
|  | Project_ID | String | PRJ-002 | Project (NULL = internal/training).
|  | Work_date | Date | 2026-07-07 | Work date.
|  | Logged_hours | Float | 6.5 | Hours logged that day.
|  | Log_category | Enum | Project | Project/Internal/Training/Admin.
|  | Task_ref | String | TASK-007 | Optional task reference (may be NULL).
DS03_Overbook_Idle_Config | 1 threshold rule (read as rule engine) | Config_ID | String | CFG-001 | Config id.
|  | Rule_name | String | SETA-08-SOP-001 | Rule set name.
|  | Overbook_threshold | Float | 1.10 | Busy > this -> Overbooked (Yellow).
|  | Overbook_red_threshold | Float | 1.20 | Busy > this -> Overbooked (Red).
|  | Idle_threshold | Float | 0.75 | Busy < this -> Idle (aligned to SOP, not 0.20).
|  | Mismatch_pct_threshold | Float | 0.20 | ¦logged-planned¦/planned > this -> mismatch.
|  | OT_max_hours_per_week | Float | 48.0 | Above this/week = OT to review.
|  | Effective_date | Date | 2026-01-01 | Effective date.
DS04_Leave_Holiday_Records | 1 leave-day of a member (or a company holiday) | Record_ID | String | LV-0002 | Record id.
|  | Member_ID | String | EMP-003 | Member (NULL = company-wide holiday).
|  | Leave_date | Date | 2026-07-06 | Date.
|  | Leave_type | Enum | Annual Leave | Annual/Sick/Maternity/Public Holiday/Training/Approved OT Comp.
|  | Approved | Bool | TRUE | TRUE = approved.
|  | Duration_days | Float | 1.0 | Days (0.5 = half day).
|  | Note | String | Full week leave | Note.
DS05_Project_Master | 1 project | Project_ID | String | PRJ-002 | Project id.
|  | Project_name | String | Energent AI | Name.
|  | Account_ID | String | ACC-B | Account/client group.
|  | Project_type | String | AI/ML Platform | Type.
|  | Status | Enum | Active | Active/On Hold/Completed/Cancelled.
|  | PM_ID | String | EMP-012 | PM (FK -> Member_Master).
|  | Start_date | Date | 2026-04-06 | Start.
|  | End_date | Date | 2026-12-31 | Planned end.
DS06_Member_Master | 1 member | Member_ID | String | EMP-009 | Member id.
|  | Full_name | String | Ly Van Minh | Name.
|  | Department | String | Frontend | Department.
|  | Role_title | String | Frontend Developer | Title.
|  | Level | String | L2 | Level L1-L7.
|  | Line_manager_id | String | EMP-004 | Manager (FK).
|  | Employment_status | Enum | Probation | Active/Probation/On Leave/Resigned.
|  | Employment | Enum | FT | FT/PT.
|  | Std_hours_week | Float | 40 | Standard hours/week (PT = 20).
|  | Join_date | Date | 2026-07-14 | Join date (drives onboarding edge).
REF_Calendar_Weeks [SHARED/REF] | 1 week of the monitoring window | Week_ID | String | W3 | Week id.
|  | Week_start | Date | 2026-07-13 | Monday.
|  | Working_days | Int | 4 | Working days (holiday reduces this).
|  | Holiday_hours_ft | Float | 8 | FT hours lost to holidays that week.
REF_KPI_Norms [SHARED/REF] | 1 RAG metric threshold (SETA-08-SOP-001) | Norm_ID | String | N01 | Norm id.
|  | Metric | String | Busy Rate | Metric.
|  | Green/Yellow/Red | String | 85-110% / ... | RAG thresholds.
Answer_Key [ANSWER KEY] | 1 finding the agent should detect (Problem 2) | Finding_ID | String | F-07 | Finding id.
|  | Entity_id | String | EMP-004 | Member/week.
|  | Issue_type | String | Overbook | Category.
|  | Expected_detection | String | Busy 125% -> rebalance | What to detect.
|  | Severity | String | High | Severity.

## DS01_Resource_Allocation
Member_ID | Project_ID | Role | Allocation_pct | Start_date | End_date | Weekly_planned_hours
EMP-001 | PRJ-001 | BE | 0.6 | 2026-06-29 | 2026-08-07 | 24
EMP-001 | PRJ-003 | BE | 0.55 | 2026-06-29 | 2026-08-07 | 22
EMP-002 | PRJ-002 | DE | 0.9 | 2026-06-29 | 2026-08-07 | 36
EMP-003 | PRJ-002 | ML | 1 | 2026-06-29 | 2026-08-07 | 40
EMP-004 | PRJ-001 | BE | 0.8 | 2026-06-29 | 2026-08-07 | 32
EMP-004 | PRJ-002 | BE | 0.45 | 2026-06-29 | 2026-08-07 | 18
EMP-005 | PRJ-001 | DevOps | 0.3 | 2026-06-29 | 2026-08-07 | 12
EMP-005 | PRJ-002 | DevOps | 0.3 | 2026-06-29 | 2026-08-07 | 12
EMP-006 | PRJ-001 | Sec | 0.95 | 2026-06-29 | 2026-08-07 | 38
EMP-007 | PRJ-002 | Design | 0.8 | 2026-06-29 | 2026-08-07 | 16
EMP-008 | PRJ-002 | BA | 0.5 | 2026-06-29 | 2026-08-07 | 20
EMP-009 | PRJ-002 | FE | 0.8 | 2026-07-13 | 2026-08-07 | 32
EMP-010 | PRJ-001 | QA | 0.6 | 2026-06-29 | 2026-08-07 | 24
EMP-010 | PRJ-002 | QA | 0.5 | 2026-06-29 | 2026-08-07 | 20
EMP-010 | PRJ-002 | QA | 0.5 | 2026-06-29 | 2026-08-07 | 20
EMP-103 | PRJ-103 | BE | 0.86 | 2026-06-29 | 2026-08-07 | 34.4
EMP-104 | PRJ-102 | BA | 0.85 | 2026-06-29 | 2026-08-07 | 34
EMP-105 | PRJ-106 | DevOps | 0.86 | 2026-06-29 | 2026-08-07 | 34.4
EMP-106 | PRJ-103 | FE | 1.01 | 2026-06-29 | 2026-08-07 | 40.4
EMP-107 | PRJ-104 | DE | 0.45 | 2026-06-29 | 2026-08-07 | 18
EMP-107 | PRJ-102 | DE | 0.5 | 2026-06-29 | 2026-08-07 | 20
EMP-108 | PRJ-102 | FE | 0.53 | 2026-06-29 | 2026-08-07 | 21.2
EMP-108 | PRJ-103 | FE | 0.39 | 2026-06-29 | 2026-08-07 | 15.6
EMP-109 | PRJ-108 | DevOps | 0.96 | 2026-06-29 | 2026-08-07 | 38.4
EMP-110 | PRJ-101 | FE | 0.56 | 2026-06-29 | 2026-08-07 | 22.4
EMP-110 | PRJ-105 | FE | 0.42 | 2026-06-29 | 2026-08-07 | 16.8
EMP-111 | PRJ-105 | BA | 1.04 | 2026-06-29 | 2026-08-07 | 41.6
EMP-112 | PRJ-105 | BA | 0.44 | 2026-06-29 | 2026-08-07 | 17.6
EMP-112 | PRJ-102 | BA | 0.6 | 2026-06-29 | 2026-08-07 | 24
EMP-113 | PRJ-106 | BE | 0.86 | 2026-06-29 | 2026-08-07 | 17.2
EMP-114 | PRJ-102 | Design | 0.43 | 2026-06-29 | 2026-08-07 | 8.6
EMP-114 | PRJ-108 | Design | 0.48 | 2026-06-29 | 2026-08-07 | 9.6
EMP-115 | PRJ-102 | Design | 0.6 | 2026-06-29 | 2026-08-07 | 24
EMP-115 | PRJ-105 | Design | 0.32 | 2026-06-29 | 2026-08-07 | 12.8
EMP-116 | PRJ-105 | QA | 0.49 | 2026-06-29 | 2026-08-07 | 19.6
EMP-116 | PRJ-104 | QA | 0.49 | 2026-06-29 | 2026-08-07 | 19.6
EMP-117 | PRJ-102 | ML | 0.49 | 2026-06-29 | 2026-08-07 | 19.6
EMP-117 | PRJ-106 | ML | 0.55 | 2026-06-29 | 2026-08-07 | 22
EMP-118 | PRJ-101 | Design | 0.48 | 2026-06-29 | 2026-08-07 | 19.2
EMP-118 | PRJ-105 | Design | 0.61 | 2026-06-29 | 2026-08-07 | 24.4

## DS02_Timesheet_Log
Member_ID | Project_ID | Work_date | Logged_hours | Log_category | Task_ref
EMP-001 | PRJ-001 | 2026-06-29 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-06-29 | 4 | Project
EMP-001 | PRJ-001 | 2026-06-30 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-06-30 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-01 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-01 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-02 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-02 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-03 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-03 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-06 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-06 | 4 | Project
EMP-001 | PRJ-001 | 2026-07-07 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-07 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-08 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-08 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-09 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-09 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-10 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-10 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-14 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-14 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-15 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-15 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-16 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-16 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-17 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-17 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-20 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-20 | 4 | Project
EMP-001 | PRJ-001 | 2026-07-21 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-21 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-22 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-22 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-23 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-23 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-24 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-24 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-27 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-27 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-28 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-07-28 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-07-29 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-29 | 5 | Project
EMP-001 | PRJ-001 | 2026-07-30 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-30 | 5 | Project
EMP-001 | PRJ-001 | 2026-07-31 | 5 | Project
EMP-001 | PRJ-003 | 2026-07-31 | 5 | Project
EMP-001 | PRJ-001 | 2026-08-03 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-08-03 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-08-04 | 4.5 | Project
EMP-001 | PRJ-003 | 2026-08-04 | 4.5 | Project
EMP-001 | PRJ-001 | 2026-08-05 | 5 | Project
EMP-001 | PRJ-003 | 2026-08-05 | 5 | Project
EMP-001 | PRJ-001 | 2026-08-06 | 5 | Project
EMP-001 | PRJ-003 | 2026-08-06 | 5 | Project
EMP-001 | PRJ-001 | 2026-08-07 | 5 | Project
EMP-001 | PRJ-003 | 2026-08-07 | 5 | Project
EMP-002 | PRJ-002 | 2026-06-29 | 4 | Project
EMP-002 | PRJ-002 | 2026-06-30 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-01 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-02 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-03 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-06 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-07 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-07-08 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-07-09 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-07-10 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-07-14 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-15 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-16 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-17 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-20 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-21 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-22 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-23 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-24 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-27 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-28 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-29 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-30 | 4 | Project
EMP-002 | PRJ-002 | 2026-07-31 | 4 | Project
EMP-002 | PRJ-002 | 2026-08-03 | 4 | Project
EMP-002 | PRJ-002 | 2026-08-04 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-08-05 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-08-06 | 3.5 | Project
EMP-002 | PRJ-002 | 2026-08-07 | 3.5 | Project
EMP-003 | PRJ-002 | 2026-06-29 | 8 | Project
EMP-003 | PRJ-002 | 2026-06-30 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-01 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-02 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-03 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-14 | 6 | Project
EMP-003 | PRJ-002 | 2026-07-15 | 6 | Project
EMP-003 | PRJ-002 | 2026-07-16 | 6 | Project
EMP-003 | PRJ-002 | 2026-07-17 | 6 | Project
EMP-003 | PRJ-002 | 2026-07-20 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-21 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-22 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-23 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-24 | 8 | Project
EMP-003 | PRJ-002 | 2026-07-27 | 10 | Project
EMP-003 | PRJ-002 | 2026-07-28 | 10.5 | Project
EMP-003 | PRJ-002 | 2026-07-29 | 10.5 | Project
EMP-003 | PRJ-002 | 2026-07-30 | 10.5 | Project
EMP-003 | PRJ-002 | 2026-07-31 | 10.5 | Project
EMP-003 | PRJ-002 | 2026-08-03 | 8 | Project
EMP-003 | PRJ-002 | 2026-08-04 | 8 | Project
EMP-003 | PRJ-002 | 2026-08-05 | 8 | Project
EMP-003 | PRJ-002 | 2026-08-06 | 8 | Project
EMP-003 | PRJ-002 | 2026-08-07 | 8 | Project
EMP-004 | PRJ-001 | 2026-06-29 | 6 | Project
EMP-004 | PRJ-002 | 2026-06-29 | 4 | Project
EMP-004 | PRJ-001 | 2026-06-30 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-06-30 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-01 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-01 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-02 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-02 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-03 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-03 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-06 | 6 | Project
EMP-004 | PRJ-002 | 2026-07-06 | 4 | Project
EMP-004 | PRJ-001 | 2026-07-07 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-07 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-08 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-08 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-09 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-09 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-10 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-10 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-14 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-14 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-15 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-15 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-16 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-16 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-17 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-17 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-20 | 6 | Project
EMP-004 | PRJ-002 | 2026-07-20 | 4 | Project
EMP-004 | PRJ-001 | 2026-07-21 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-21 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-22 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-22 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-23 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-23 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-24 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-24 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-27 | 6 | Project
EMP-004 | PRJ-002 | 2026-07-27 | 4 | Project
EMP-004 | PRJ-001 | 2026-07-28 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-28 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-29 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-29 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-30 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-30 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-07-31 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-07-31 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-08-03 | 6 | Project
EMP-004 | PRJ-002 | 2026-08-03 | 4 | Project
EMP-004 | PRJ-001 | 2026-08-04 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-08-04 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-08-05 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-08-05 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-08-06 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-08-06 | 3.5 | Project
EMP-004 | PRJ-001 | 2026-08-07 | 6.5 | Project
EMP-004 | PRJ-002 | 2026-08-07 | 3.5 | Project
EMP-005 | PRJ-001 | 2026-06-29 | 2 | Project
EMP-005 | PRJ-002 | 2026-06-29 | 2 | Project
EMP-005 | PRJ-001 | 2026-06-30 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-06-30 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-01 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-01 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-02 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-02 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-03 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-03 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-06 | 2 | Project
EMP-005 | PRJ-002 | 2026-07-06 | 2 | Project
EMP-005 | PRJ-001 | 2026-07-07 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-07 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-08 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-08 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-09 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-09 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-10 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-10 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-14 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-14 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-15 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-15 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-16 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-16 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-17 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-17 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-20 | 2 | Project
EMP-005 | PRJ-002 | 2026-07-20 | 2 | Project
EMP-005 | PRJ-001 | 2026-07-21 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-21 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-22 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-22 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-23 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-23 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-24 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-24 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-27 | 2 | Project
EMP-005 | PRJ-002 | 2026-07-27 | 2 | Project
EMP-005 | PRJ-001 | 2026-07-28 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-28 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-29 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-29 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-30 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-30 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-07-31 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-07-31 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-08-03 | 2 | Project
EMP-005 | PRJ-002 | 2026-08-03 | 2 | Project
EMP-005 | PRJ-001 | 2026-08-04 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-08-04 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-08-05 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-08-05 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-08-06 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-08-06 | 2.5 | Project
EMP-005 | PRJ-001 | 2026-08-07 | 2.5 | Project
EMP-005 | PRJ-002 | 2026-08-07 | 2.5 | Project
EMP-006 | PRJ-001 | 2026-06-29 | 10 | Project
EMP-006 | PRJ-001 | 2026-06-30 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-01 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-02 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-03 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-06 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-07 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-08 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-09 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-10 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-14 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-15 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-16 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-17 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-20 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-21 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-22 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-23 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-24 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-07-27 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-28 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-29 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-30 | 10 | Project
EMP-006 | PRJ-001 | 2026-07-31 | 10 | Project
EMP-006 | PRJ-001 | 2026-08-03 | 10 | Project
EMP-006 | PRJ-001 | 2026-08-04 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-08-05 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-08-06 | 9.5 | Project
EMP-006 | PRJ-001 | 2026-08-07 | 9.5 | Project
EMP-007 | PRJ-002 | 2026-06-29 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-06-30 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-01 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-02 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-03 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-06 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-07 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-08 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-09 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-10 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-14 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-15 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-16 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-17 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-20 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-21 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-22 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-23 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-24 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-27 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-28 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-07-29 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-30 | 3 | Project
EMP-007 | PRJ-002 | 2026-07-31 | 3 | Project
EMP-007 | PRJ-002 | 2026-08-03 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-08-04 | 3.5 | Project
EMP-007 | PRJ-002 | 2026-08-05 | 3 | Project
EMP-007 | PRJ-002 | 2026-08-06 | 3 | Project
EMP-007 | PRJ-002 | 2026-08-07 | 3 | Project
EMP-008 | PRJ-002 | 2026-06-29 | 4 | Project
EMP-008 | PRJ-002 | 2026-06-30 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-01 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-02 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-03 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-06 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-07 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-08 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-09 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-10 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-14 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-15 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-16 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-17 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-20 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-21 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-22 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-23 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-24 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-27 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-28 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-29 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-30 | 4 | Project
EMP-008 | PRJ-002 | 2026-07-31 | 4 | Project
EMP-008 | PRJ-002 | 2026-08-03 | 4 | Project
EMP-008 | PRJ-002 | 2026-08-04 | 4 | Project
EMP-008 | PRJ-002 | 2026-08-05 | 4 | Project
EMP-008 | PRJ-002 | 2026-08-06 | 4 | Project
EMP-008 | PRJ-002 | 2026-08-07 | 4 | Project
EMP-009 |  | 2026-07-14 | 6 | Training
EMP-009 |  | 2026-07-15 | 6 | Training
EMP-009 |  | 2026-07-16 | 6 | Training
EMP-009 |  | 2026-07-17 | 6 | Training
EMP-009 | PRJ-002 | 2026-07-20 | 6 | Project
EMP-009 | PRJ-002 | 2026-07-21 | 5.5 | Project
EMP-009 | PRJ-002 | 2026-07-22 | 5.5 | Project
EMP-009 | PRJ-002 | 2026-07-23 | 5.5 | Project
EMP-009 | PRJ-002 | 2026-07-24 | 5.5 | Project
EMP-009 | PRJ-002 | 2026-07-27 | 6 | Project
EMP-009 | PRJ-002 | 2026-07-28 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-07-29 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-07-30 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-07-31 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-08-03 | 6 | Project
EMP-009 | PRJ-002 | 2026-08-04 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-08-05 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-08-06 | 6.5 | Project
EMP-009 | PRJ-002 | 2026-08-07 | 6.5 | Project
EMP-010 | PRJ-001 | 2026-06-29 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-06-29 | 4 | Project
EMP-010 | PRJ-001 | 2026-06-30 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-06-30 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-01 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-01 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-02 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-02 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-03 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-03 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-06 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-06 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-07 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-07 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-08 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-08 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-09 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-09 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-10 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-10 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-14 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-14 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-15 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-15 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-16 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-16 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-17 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-17 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-20 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-20 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-21 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-21 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-22 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-22 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-23 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-23 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-24 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-24 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-27 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-27 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-28 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-07-28 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-29 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-29 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-30 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-30 | 4 | Project
EMP-010 | PRJ-001 | 2026-07-31 | 5 | Project
EMP-010 | PRJ-002 | 2026-07-31 | 4 | Project
EMP-010 | PRJ-001 | 2026-08-03 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-08-03 | 4 | Project
EMP-010 | PRJ-001 | 2026-08-04 | 4.5 | Project
EMP-010 | PRJ-002 | 2026-08-04 | 4 | Project
EMP-010 | PRJ-001 | 2026-08-05 | 5 | Project
EMP-010 | PRJ-002 | 2026-08-05 | 4 | Project
EMP-010 | PRJ-001 | 2026-08-06 | 5 | Project
EMP-010 | PRJ-002 | 2026-08-06 | 4 | Project
EMP-010 | PRJ-001 | 2026-08-07 | 5 | Project
EMP-010 | PRJ-002 | 2026-08-07 | 4 | Project
EMP-103 | PRJ-103 | 2026-06-29 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-06-30 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-01 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-02 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-03 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-06 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-07 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-08 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-09 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-10 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-14 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-15 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-16 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-17 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-20 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-21 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-22 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-23 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-24 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-27 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-28 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-07-29 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-30 | 7 | Project
EMP-103 | PRJ-103 | 2026-07-31 | 7 | Project
EMP-103 | PRJ-103 | 2026-08-03 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-08-04 | 7.5 | Project
EMP-103 | PRJ-103 | 2026-08-05 | 7 | Project
EMP-103 | PRJ-103 | 2026-08-06 | 7 | Project
EMP-103 | PRJ-103 | 2026-08-07 | 7 | Project
EMP-104 | PRJ-102 | 2026-06-29 | 7 | Project
EMP-104 | PRJ-102 | 2026-06-30 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-01 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-02 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-03 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-06 | 7 | Project
EMP-104 | PRJ-102 | 2026-07-07 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-08 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-09 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-10 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-14 | 7 | Project
EMP-104 | PRJ-102 | 2026-07-15 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-16 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-17 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-20 | 7 | Project
EMP-104 | PRJ-102 | 2026-07-21 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-22 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-23 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-24 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-27 | 7 | Project
EMP-104 | PRJ-102 | 2026-07-28 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-29 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-30 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-07-31 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-08-03 | 7 | Project
EMP-104 | PRJ-102 | 2026-08-04 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-08-05 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-08-06 | 6.5 | Project
EMP-104 | PRJ-102 | 2026-08-07 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-06-29 | 7 | Project
EMP-105 | PRJ-106 | 2026-06-30 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-01 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-02 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-03 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-06 | 7 | Project
EMP-105 | PRJ-106 | 2026-07-07 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-08 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-09 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-10 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-14 | 7 | Project
EMP-105 | PRJ-106 | 2026-07-15 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-16 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-17 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-20 | 7 | Project
EMP-105 | PRJ-106 | 2026-07-21 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-22 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-23 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-24 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-27 | 7 | Project
EMP-105 | PRJ-106 | 2026-07-28 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-29 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-30 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-07-31 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-08-03 | 7 | Project
EMP-105 | PRJ-106 | 2026-08-04 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-08-05 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-08-06 | 6.5 | Project
EMP-105 | PRJ-106 | 2026-08-07 | 6.5 | Project
EMP-106 | PRJ-103 | 2026-06-29 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-06-30 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-01 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-02 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-03 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-06 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-07 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-08 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-09 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-10 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-14 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-15 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-16 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-17 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-20 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-21 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-22 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-23 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-24 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-27 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-28 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-07-29 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-30 | 8 | Project
EMP-106 | PRJ-103 | 2026-07-31 | 8 | Project
EMP-106 | PRJ-103 | 2026-08-03 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-08-04 | 7.5 | Project
EMP-106 | PRJ-103 | 2026-08-05 | 8 | Project
EMP-106 | PRJ-103 | 2026-08-06 | 8 | Project
EMP-106 | PRJ-103 | 2026-08-07 | 8 | Project
EMP-107 | PRJ-102 | 2026-06-29 | 4 | Project
EMP-107 | PRJ-104 | 2026-06-29 | 3 | Project
EMP-107 | PRJ-102 | 2026-06-30 | 4 | Project
EMP-107 | PRJ-104 | 2026-06-30 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-01 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-01 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-02 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-02 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-03 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-03 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-06 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-06 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-07 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-07 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-08 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-08 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-09 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-09 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-10 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-10 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-14 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-14 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-15 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-15 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-16 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-16 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-17 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-17 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-20 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-20 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-21 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-21 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-22 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-22 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-23 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-23 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-24 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-24 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-27 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-27 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-28 | 4 | Project
EMP-107 | PRJ-104 | 2026-07-28 | 3 | Project
EMP-107 | PRJ-102 | 2026-07-29 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-29 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-30 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-30 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-07-31 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-07-31 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-08-03 | 4 | Project
EMP-107 | PRJ-104 | 2026-08-03 | 3 | Project
EMP-107 | PRJ-102 | 2026-08-04 | 4 | Project
EMP-107 | PRJ-104 | 2026-08-04 | 3 | Project
EMP-107 | PRJ-102 | 2026-08-05 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-08-05 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-08-06 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-08-06 | 3.5 | Project
EMP-107 | PRJ-102 | 2026-08-07 | 3.5 | Project
EMP-107 | PRJ-104 | 2026-08-07 | 3.5 | Project
EMP-108 | PRJ-102 | 2026-06-29 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-06-29 | 3 | Project
EMP-108 | PRJ-102 | 2026-06-30 | 4 | Project
EMP-108 | PRJ-103 | 2026-06-30 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-01 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-01 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-02 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-02 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-03 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-03 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-06 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-07-06 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-07 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-07 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-08 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-08 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-09 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-09 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-10 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-10 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-14 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-07-14 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-15 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-15 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-16 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-16 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-17 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-17 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-20 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-07-20 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-21 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-21 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-22 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-22 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-23 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-23 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-24 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-24 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-27 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-07-27 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-28 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-28 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-29 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-29 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-30 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-30 | 3 | Project
EMP-108 | PRJ-102 | 2026-07-31 | 4 | Project
EMP-108 | PRJ-103 | 2026-07-31 | 3 | Project
EMP-108 | PRJ-102 | 2026-08-03 | 3.5 | Project
EMP-108 | PRJ-103 | 2026-08-03 | 3 | Project
EMP-108 | PRJ-102 | 2026-08-04 | 4 | Project
EMP-108 | PRJ-103 | 2026-08-04 | 3 | Project
EMP-108 | PRJ-102 | 2026-08-05 | 4 | Project
EMP-108 | PRJ-103 | 2026-08-05 | 3 | Project
EMP-108 | PRJ-102 | 2026-08-06 | 4 | Project
EMP-108 | PRJ-103 | 2026-08-06 | 3 | Project
EMP-108 | PRJ-102 | 2026-08-07 | 4 | Project
EMP-108 | PRJ-103 | 2026-08-07 | 3 | Project
EMP-109 | PRJ-108 | 2026-06-29 | 8.5 | Project
EMP-109 | PRJ-108 | 2026-06-30 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-01 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-02 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-03 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-06 | 8.5 | Project
EMP-109 | PRJ-108 | 2026-07-07 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-08 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-09 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-10 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-14 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-15 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-16 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-17 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-20 | 8.5 | Project
EMP-109 | PRJ-108 | 2026-07-21 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-22 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-23 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-24 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-27 | 8.5 | Project
EMP-109 | PRJ-108 | 2026-07-28 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-29 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-30 | 8 | Project
EMP-109 | PRJ-108 | 2026-07-31 | 8 | Project
EMP-109 | PRJ-108 | 2026-08-03 | 8.5 | Project
EMP-109 | PRJ-108 | 2026-08-04 | 8 | Project
EMP-109 | PRJ-108 | 2026-08-05 | 8 | Project
EMP-109 | PRJ-108 | 2026-08-06 | 8 | Project
EMP-109 | PRJ-108 | 2026-08-07 | 8 | Project
EMP-110 | PRJ-101 | 2026-06-29 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-06-29 | 3 | Project
EMP-110 | PRJ-101 | 2026-06-30 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-06-30 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-01 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-01 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-02 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-02 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-03 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-03 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-06 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-06 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-07 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-07 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-08 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-08 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-09 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-09 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-10 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-10 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-14 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-14 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-15 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-15 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-16 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-16 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-17 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-17 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-20 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-20 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-21 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-21 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-22 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-22 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-23 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-23 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-24 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-24 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-27 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-27 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-28 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-07-28 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-29 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-29 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-30 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-30 | 3 | Project
EMP-110 | PRJ-101 | 2026-07-31 | 4 | Project
EMP-110 | PRJ-105 | 2026-07-31 | 3 | Project
EMP-110 | PRJ-101 | 2026-08-03 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-08-03 | 3 | Project
EMP-110 | PRJ-101 | 2026-08-04 | 4.5 | Project
EMP-110 | PRJ-105 | 2026-08-04 | 3 | Project
EMP-110 | PRJ-101 | 2026-08-05 | 4 | Project
EMP-110 | PRJ-105 | 2026-08-05 | 3 | Project
EMP-110 | PRJ-101 | 2026-08-06 | 4 | Project
EMP-110 | PRJ-105 | 2026-08-06 | 3 | Project
EMP-110 | PRJ-101 | 2026-08-07 | 4 | Project
EMP-110 | PRJ-105 | 2026-08-07 | 3 | Project
EMP-111 | PRJ-105 | 2026-06-29 | 8 | Project
EMP-111 | PRJ-105 | 2026-06-30 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-01 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-02 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-03 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-06 | 8 | Project
EMP-111 | PRJ-105 | 2026-07-07 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-08 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-09 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-10 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-14 | 8 | Project
EMP-111 | PRJ-105 | 2026-07-15 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-16 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-17 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-20 | 8 | Project
EMP-111 | PRJ-105 | 2026-07-21 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-22 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-23 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-24 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-27 | 8 | Project
EMP-111 | PRJ-105 | 2026-07-28 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-29 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-30 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-07-31 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-08-03 | 8 | Project
EMP-111 | PRJ-105 | 2026-08-04 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-08-05 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-08-06 | 7.5 | Project
EMP-111 | PRJ-105 | 2026-08-07 | 7.5 | Project
EMP-112 | PRJ-102 | 2026-06-29 | 5 | Project
EMP-112 | PRJ-105 | 2026-06-29 | 4 | Project
EMP-112 | PRJ-102 | 2026-06-30 | 5 | Project
EMP-112 | PRJ-105 | 2026-06-30 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-01 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-01 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-02 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-02 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-03 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-03 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-06 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-06 | 4 | Project
EMP-112 | PRJ-102 | 2026-07-07 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-07 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-08 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-08 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-09 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-09 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-10 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-10 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-14 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-14 | 4 | Project
EMP-112 | PRJ-102 | 2026-07-15 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-15 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-16 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-16 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-17 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-17 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-20 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-20 | 4 | Project
EMP-112 | PRJ-102 | 2026-07-21 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-21 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-22 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-22 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-23 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-23 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-24 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-24 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-27 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-27 | 4 | Project
EMP-112 | PRJ-102 | 2026-07-28 | 5 | Project
EMP-112 | PRJ-105 | 2026-07-28 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-29 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-29 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-30 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-30 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-07-31 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-07-31 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-08-03 | 5 | Project
EMP-112 | PRJ-105 | 2026-08-03 | 4 | Project
EMP-112 | PRJ-102 | 2026-08-04 | 5 | Project
EMP-112 | PRJ-105 | 2026-08-04 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-08-05 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-08-05 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-08-06 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-08-06 | 3.5 | Project
EMP-112 | PRJ-102 | 2026-08-07 | 4.5 | Project
EMP-112 | PRJ-105 | 2026-08-07 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-06-29 | 3 | Project
EMP-113 | PRJ-106 | 2026-06-30 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-01 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-02 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-03 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-06 | 3 | Project
EMP-113 | PRJ-106 | 2026-07-07 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-08 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-09 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-10 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-14 | 3 | Project
EMP-113 | PRJ-106 | 2026-07-15 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-16 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-17 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-20 | 3 | Project
EMP-113 | PRJ-106 | 2026-07-21 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-22 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-23 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-24 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-27 | 3 | Project
EMP-113 | PRJ-106 | 2026-07-28 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-29 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-30 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-07-31 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-08-03 | 3 | Project
EMP-113 | PRJ-106 | 2026-08-04 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-08-05 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-08-06 | 3.5 | Project
EMP-113 | PRJ-106 | 2026-08-07 | 3.5 | Project
EMP-114 | PRJ-102 | 2026-06-29 | 2 | Project
EMP-114 | PRJ-108 | 2026-06-29 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-06-30 | 2 | Project
EMP-114 | PRJ-108 | 2026-06-30 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-01 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-01 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-02 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-02 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-03 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-03 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-06 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-06 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-07 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-07 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-08 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-08 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-09 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-09 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-10 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-10 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-14 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-14 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-15 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-15 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-16 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-16 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-17 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-17 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-20 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-20 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-21 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-21 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-22 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-22 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-23 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-23 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-24 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-24 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-27 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-27 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-28 | 2 | Project
EMP-114 | PRJ-108 | 2026-07-28 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-07-29 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-29 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-30 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-30 | 2 | Project
EMP-114 | PRJ-102 | 2026-07-31 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-07-31 | 2 | Project
EMP-114 | PRJ-102 | 2026-08-03 | 2 | Project
EMP-114 | PRJ-108 | 2026-08-03 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-08-04 | 2 | Project
EMP-114 | PRJ-108 | 2026-08-04 | 1.5 | Project
EMP-114 | PRJ-102 | 2026-08-05 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-08-05 | 2 | Project
EMP-114 | PRJ-102 | 2026-08-06 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-08-06 | 2 | Project
EMP-114 | PRJ-102 | 2026-08-07 | 1.5 | Project
EMP-114 | PRJ-108 | 2026-08-07 | 2 | Project
EMP-115 | PRJ-102 | 2026-06-29 | 5 | Project
EMP-115 | PRJ-105 | 2026-06-29 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-06-30 | 5 | Project
EMP-115 | PRJ-105 | 2026-06-30 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-01 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-01 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-02 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-02 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-03 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-03 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-06 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-06 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-07 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-07 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-08 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-08 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-09 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-09 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-10 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-10 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-14 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-14 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-15 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-15 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-16 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-16 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-17 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-17 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-20 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-20 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-21 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-21 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-22 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-22 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-23 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-23 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-24 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-24 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-27 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-27 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-28 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-28 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-29 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-29 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-30 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-30 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-07-31 | 5 | Project
EMP-115 | PRJ-105 | 2026-07-31 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-08-03 | 5 | Project
EMP-115 | PRJ-105 | 2026-08-03 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-08-04 | 5 | Project
EMP-115 | PRJ-105 | 2026-08-04 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-08-05 | 5 | Project
EMP-115 | PRJ-105 | 2026-08-05 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-08-06 | 5 | Project
EMP-115 | PRJ-105 | 2026-08-06 | 2.5 | Project
EMP-115 | PRJ-102 | 2026-08-07 | 5 | Project
EMP-115 | PRJ-105 | 2026-08-07 | 2.5 | Project
EMP-116 | PRJ-104 | 2026-06-29 | 4 | Project
EMP-116 | PRJ-105 | 2026-06-29 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-06-30 | 4 | Project
EMP-116 | PRJ-105 | 2026-06-30 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-01 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-01 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-02 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-02 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-03 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-03 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-06 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-06 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-07 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-07 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-08 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-08 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-09 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-09 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-10 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-10 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-14 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-14 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-15 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-15 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-16 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-16 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-17 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-17 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-20 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-20 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-21 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-21 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-22 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-22 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-23 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-23 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-24 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-24 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-27 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-27 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-28 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-28 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-07-29 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-29 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-30 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-30 | 4 | Project
EMP-116 | PRJ-104 | 2026-07-31 | 4 | Project
EMP-116 | PRJ-105 | 2026-07-31 | 4 | Project
EMP-116 | PRJ-104 | 2026-08-03 | 4 | Project
EMP-116 | PRJ-105 | 2026-08-03 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-08-04 | 4 | Project
EMP-116 | PRJ-105 | 2026-08-04 | 3.5 | Project
EMP-116 | PRJ-104 | 2026-08-05 | 4 | Project
EMP-116 | PRJ-105 | 2026-08-05 | 4 | Project
EMP-116 | PRJ-104 | 2026-08-06 | 4 | Project
EMP-116 | PRJ-105 | 2026-08-06 | 4 | Project
EMP-116 | PRJ-104 | 2026-08-07 | 4 | Project
EMP-116 | PRJ-105 | 2026-08-07 | 4 | Project
EMP-117 | PRJ-102 | 2026-06-29 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-06-29 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-06-30 | 4 | Project
EMP-117 | PRJ-106 | 2026-06-30 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-01 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-01 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-02 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-02 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-03 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-03 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-06 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-07-06 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-07 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-07 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-08 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-08 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-09 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-09 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-10 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-10 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-14 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-07-14 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-15 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-15 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-16 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-16 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-17 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-17 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-20 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-07-20 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-21 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-21 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-22 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-22 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-23 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-23 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-24 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-24 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-27 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-07-27 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-28 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-28 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-29 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-29 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-30 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-30 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-07-31 | 4 | Project
EMP-117 | PRJ-106 | 2026-07-31 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-08-03 | 3.5 | Project
EMP-117 | PRJ-106 | 2026-08-03 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-08-04 | 4 | Project
EMP-117 | PRJ-106 | 2026-08-04 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-08-05 | 4 | Project
EMP-117 | PRJ-106 | 2026-08-05 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-08-06 | 4 | Project
EMP-117 | PRJ-106 | 2026-08-06 | 4.5 | Project
EMP-117 | PRJ-102 | 2026-08-07 | 4 | Project
EMP-117 | PRJ-106 | 2026-08-07 | 4.5 | Project
EMP-118 | PRJ-101 | 2026-06-29 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-06-29 | 5 | Project
EMP-118 | PRJ-101 | 2026-06-30 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-06-30 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-01 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-01 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-02 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-02 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-03 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-03 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-06 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-06 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-07 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-07 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-08 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-08 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-09 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-09 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-10 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-10 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-14 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-14 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-15 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-15 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-16 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-16 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-17 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-17 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-20 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-20 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-21 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-21 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-22 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-22 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-23 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-23 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-24 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-24 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-27 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-27 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-28 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-07-28 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-29 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-29 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-30 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-30 | 5 | Project
EMP-118 | PRJ-101 | 2026-07-31 | 4 | Project
EMP-118 | PRJ-105 | 2026-07-31 | 5 | Project
EMP-118 | PRJ-101 | 2026-08-03 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-08-03 | 5 | Project
EMP-118 | PRJ-101 | 2026-08-04 | 3.5 | Project
EMP-118 | PRJ-105 | 2026-08-04 | 5 | Project
EMP-118 | PRJ-101 | 2026-08-05 | 4 | Project
EMP-118 | PRJ-105 | 2026-08-05 | 5 | Project
EMP-118 | PRJ-101 | 2026-08-06 | 4 | Project
EMP-118 | PRJ-105 | 2026-08-06 | 5 | Project
EMP-118 | PRJ-101 | 2026-08-07 | 4 | Project
EMP-118 | PRJ-105 | 2026-08-07 | 5 | Project

## DS03_Overbook_Idle_Config
Config_ID | Rule_name | Overbook_threshold | Overbook_red_threshold | Idle_threshold | Mismatch_pct_threshold | OT_max_hours_per_week | Effective_date
CFG-001 | SETA-08-SOP-001 RAG thresholds | 1.1 | 1.2 | 0.75 | 0.2 | 48 | 2026-01-01

## DS04_Leave_Holiday_Records
Record_ID | Member_ID | Leave_date | Leave_type | Approved | Duration_days | Note
LV-0001 |  | 2026-07-13 | Public Holiday | TRUE | 1 | Company-wide holiday
LV-0002 | EMP-003 | 2026-07-06 | Annual Leave | TRUE | 1 | Approved annual leave (full week)
LV-0003 | EMP-003 | 2026-07-07 | Annual Leave | TRUE | 1 | Approved annual leave (full week)
LV-0004 | EMP-003 | 2026-07-08 | Annual Leave | TRUE | 1 | Approved annual leave (full week)
LV-0005 | EMP-003 | 2026-07-09 | Annual Leave | TRUE | 1 | Approved annual leave (full week)
LV-0006 | EMP-003 | 2026-07-10 | Annual Leave | TRUE | 1 | Approved annual leave (full week)
LV-0007 | EMP-003 | 2026-07-27 | Approved OT Comp | TRUE | 1 | Approved OT — exclude from over-log flag
LV-0008 | EMP-003 | 2026-07-28 | Approved OT Comp | TRUE | 1 | Approved OT — exclude from over-log flag
LV-0009 | EMP-009 | 2026-07-14 | Training | TRUE | 1 | Onboarding training (also logged in timesheet)
LV-0010 | EMP-009 | 2026-07-15 | Training | TRUE | 1 | Onboarding training (also logged in timesheet)
LV-0011 | EMP-009 | 2026-07-16 | Training | TRUE | 1 | Onboarding training (also logged in timesheet)

## DS05_Project_Master
Shared master — identical rows appear in PMO_01 file.
Project_ID | Project_name | Account_ID | Project_type | Status | PM_ID | Start_date | End_date
PRJ-001 | Project Orion (Core Banking) | ACC-A | Software/Migration | Active | EMP-012 | 2026-05-19 | 2026-12-19
PRJ-002 | Energent AI (Data Platform) | ACC-B | AI/ML Platform | Active | EMP-012 | 2026-04-06 | 2026-12-31
PRJ-003 | Project Titan (Internal Tools) | ACC-A | Software | Active | EMP-011 | 2026-06-01 | 2026-10-31
PRJ-H-101 | Mercury Core Migration | ACC-A | Software/Migration | Completed | EMP-012 | 2025-01-06 | 2025-09-05
PRJ-H-102 | Saturn Banking Upgrade | ACC-A | Software/Migration | Completed | EMP-012 | 2025-02-03 | 2025-09-01
PRJ-H-103 | Comet ML Pipeline | ACC-B | AI/ML Platform | Completed | EMP-011 | 2024-10-07 | 2025-07-07
PRJ-H-104 | Nebula Forecast Engine | ACC-B | AI/ML Platform | Completed | EMP-011 | 2024-11-04 | 2025-07-21
PRJ-H-105 | Pulsar CRM | ACC-C | Software | Completed | EMP-012 | 2025-03-03 | 2025-07-01
PRJ-H-199 | Flux POC | ACC-C | AI/ML Platform | Completed | EMP-011 | 2025-05-01 | 2025-05-16
PRJ-101 | Project Apollo | ACC-E | Software/Migration | Active | EMP-012 | 2026-04-05 | 2026-09-12
PRJ-102 | Project Vega | ACC-C | Software | Active | EMP-101 | 2026-04-11 | 2026-11-11
PRJ-103 | Project Lyra | ACC-C | Software/Migration | Active | EMP-012 | 2026-03-08 | 2026-10-16
PRJ-104 | Project Draco | ACC-B | Integration | Active | EMP-101 | 2026-04-27 | 2026-12-06
PRJ-105 | Project Orbit | ACC-D | Integration | Active | EMP-101 | 2026-06-21 | 2026-11-05
PRJ-106 | Project Helios | ACC-A | Software/Migration | Active | EMP-102 | 2026-03-28 | 2026-10-26
PRJ-107 | Project Atlas | ACC-A | Mobile | Active | EMP-012 | 2026-03-23 | 2026-10-09
PRJ-108 | Project Zephyr | ACC-A | Data | Active | EMP-102 | 2026-06-07 | 2026-11-08
PRJ-H-201 | Project Zephyr (archived) | ACC-E | Software/Migration | Completed | EMP-012 | 2024-04-28 | 2025-02-15
PRJ-H-202 | Project Cobalt (archived) | ACC-C | Software/Migration | Completed | EMP-011 | 2024-04-27 | 2025-01-15
PRJ-H-203 | Project Quartz (archived) | ACC-C | Software | Completed | EMP-102 | 2024-08-24 | 2025-09-16
PRJ-H-204 | Project Nimbus (archived) | ACC-B | Data | Completed | EMP-011 | 2024-03-12 | 2025-03-02
PRJ-H-205 | Project Cedar (archived) | ACC-D | Software | Completed | EMP-012 | 2024-04-04 | 2025-07-04
PRJ-H-206 | Project Falcon (archived) | ACC-A | Integration | Completed | EMP-101 | 2024-07-05 | 2025-08-07

## DS06_Member_Master
Shared master — identical rows appear in PMO_01 file.
Member_ID | Full_name | Department | Role_title | Level | Line_manager_id | Employment_status | Employment | Std_hours_week | Join_date
EMP-001 | Nguyen Van An | Backend | Backend Developer | L3 | EMP-004 | Active | FT | 40 | 2023-03-01
EMP-002 | Tran Thi Bich | Data | Data Engineer | L3 | EMP-011 | Active | FT | 40 | 2022-09-12
EMP-003 | Le Van Cuong | AI/ML | ML Engineer | L4 | EMP-011 | Active | FT | 40 | 2021-06-01
EMP-004 | Pham Thi Dung | Backend | Backend Lead | L5 | EMP-011 | Active | FT | 40 | 2019-02-18
EMP-005 | Hoang Van Em | Platform | DevOps Engineer | L4 | EMP-011 | Active | FT | 40 | 2022-01-10
EMP-006 | Do Van Khoa | Security | Security Engineer | L4 | EMP-011 | Active | FT | 40 | 2020-11-03
EMP-007 | Bui Thi Hoa | Design | UX/UI Designer | L3 | EMP-012 | Active | PT | 20 | 2023-08-21
EMP-008 | Ngo Thi Lan | BA | Business Analyst | L3 | EMP-012 | Active | FT | 40 | 2022-04-04
EMP-009 | Ly Van Minh | Frontend | Frontend Developer | L2 | EMP-004 | Probation | FT | 40 | 2026-07-14
EMP-010 | Truong Thi Nga | QA | QA Engineer | L3 | EMP-004 | Active | FT | 40 | 2021-10-07
EMP-011 | Vu Thi Mai | Engineering | Engineering Manager | L6 | EMP-012 | Active | FT | 40 | 2017-05-02
EMP-012 | Dang Van Phuc | PMO | PMO Lead / PM | L6 |  | Active | FT | 40 | 2016-01-15
EMP-101 | Le Anh Tuan | PMO | Project Manager | L5 | EMP-101 | Active | FT | 40 | 2019-09-28
EMP-102 | Dao Chi Nam | PMO | Project Manager | L5 | EMP-011 | Active | FT | 40 | 2019-07-23
EMP-103 | Hoang Hieu Nam | Backend | Backend Developer | L3 | EMP-011 | Active | FT | 40 | 2020-11-01
EMP-104 | Do My Quan | BA | Business Analyst | L4 | EMP-101 | Active | FT | 40 | 2024-08-06
EMP-105 | Do Trang Binh | Platform | DevOps Engineer | L2 | EMP-101 | Active | FT | 40 | 2020-03-11
EMP-106 | Do Yen Quynh | Frontend | Frontend Developer | L5 | EMP-101 | Active | FT | 40 | 2024-12-06
EMP-107 | Ho Hung Thao | Data | Data Engineer | L3 | EMP-101 | Active | FT | 40 | 2023-07-06
EMP-108 | Phan Nhung My | Frontend | Frontend Developer | L3 | EMP-011 | Active | FT | 40 | 2020-10-28
EMP-109 | Phan Ha Ha | Platform | DevOps Engineer | L5 | EMP-011 | Active | FT | 40 | 2023-01-21
EMP-110 | Pham Trang Anh | Frontend | Frontend Developer | L4 | EMP-011 | Active | FT | 40 | 2021-05-11
EMP-111 | Do Anh Hieu | BA | Business Analyst | L4 | EMP-102 | Active | FT | 40 | 2020-02-03
EMP-112 | Ngo Tuan Hieu | BA | Business Analyst | L3 | EMP-012 | Active | FT | 40 | 2024-01-11
EMP-113 | Pham Ha Viet | Backend | Backend Developer | L2 | EMP-101 | Active | PT | 20 | 2018-11-15
EMP-114 | Tran Long Giang | Design | UX/UI Designer | L5 | EMP-012 | Active | PT | 20 | 2023-02-04
EMP-115 | Cao Nam Long | Design | UX/UI Designer | L5 | EMP-011 | Active | FT | 40 | 2020-02-19
EMP-116 | Cao Ngan Thao | QA | QA Engineer | L4 | EMP-012 | Active | FT | 40 | 2024-06-01
EMP-117 | Duong Dat Chi | AI/ML | ML Engineer | L4 | EMP-101 | Active | FT | 40 | 2021-01-08
EMP-118 | Duong Nhung Binh | Design | UX/UI Designer | L3 | EMP-101 | Active | FT | 40 | 2024-01-19

## REF_Calendar_Weeks
Week_ID | Week_start | Week_end | Working_days | Holiday_hours_ft | Note
W1 | 2026-06-29 | 2026-07-03 | 5 | 0
W2 | 2026-07-06 | 2026-07-10 | 5 | 0
W3 | 2026-07-13 | 2026-07-17 | 4 | 8 | Company public holiday Mon 2026-07-13 → 4 working days
W4 | 2026-07-20 | 2026-07-24 | 5 | 0
W5 | 2026-07-27 | 2026-07-31 | 5 | 0
W6 | 2026-08-03 | 2026-08-07 | 5 | 0

## REF_KPI_Norms
Norm_ID | Metric | Formula | Green | Yellow | Red | Used_for
N01 | Busy Rate | Planned_h / Available_h | 85-110% | 111-119% | >120% or <75% | Overbook/Idle — Problem 2 + feasibility Problem 1
N02 | Utilization Rate | Worked_h / Available_h | 75-90% | 60-74% / 91-100% | <60% or >100% | Real intensity; >100% burnout — Problem 2
N03 | Billable Rate | Billable_h / Worked_h | >=80% | 70-79% | <70% | Revenue-generating hours — Problem 2
N04 | Bench Rate | Bench_h / Available_h | <=10% | 11-20% | >20% | Unassigned capacity — Problem 2 (idle)
N05 | Overtime Ratio | OT_h / Standard_h | <=5% | 6-15% | >15% | Leading burnout — Problem 2 (OT edge)
N06 | Effort Consumption | Actual_h / Planned_h | 85-110% | 75-84% / 111-119% | <=75% or >=120% | RA vs Timesheet mismatch — Problem 2 + Problem 1
N07 | On-time Delivery | On-time_MS / Total_MS | >=90% | 70-89% | <70% | Benchmark feasibility — Problem 1
N08 | SPI | EV / PV | 0.95-1.05 | 0.85-0.94 / 1.06-1.15 | <0.85 or >1.15 | Schedule realism — Problem 1
N09 | Velocity Variance | StdDev(5 sprint)/Avg | <=15% | 16-25% | >25% | Forecast reliability — Problem 1
N10 | THI | Non-dev_h / Total_h | 15-25% | 10-14% / 26-35% | <10% or >35% | Tech-debt prevention budget — Problem 1
N11 | Risk Closure Rate | Risks_closed / Total | >=80% | 60-79% | <60% | Whether RAID is alive — Problem 1
N12 | Training Compliance | Done / Required | 100% | 85-99% | <85% | Valid edge case (training) — Problem 2

## Answer_Key
Case_ID | 07_onboarding_missing_weeks
Description | Member joins mid-range with missing earlier timesheets and allocations.
Finding_ID | Entity_type | Entity_id | Issue_type | Week_ID | Expected_detection | Severity
07_onboarding_missing_weeks-F01 | Member | EMP-009 | edge_onboard_missing | W1 | Member joins mid-range with missing earlier timesheets and allocations. | Info
07_onboarding_missing_weeks-F02 | Member | EMP-009 | edge_onboard_missing | W2 | Member joins mid-range with missing earlier timesheets and allocations. | Info
Recommendation_ID | Source_member_id | Week_ID | Expected_status | Expected_top_targets
Data_quality_degraded | false
Required_flags
Eval_prompts
Ingest 07_onboarding_missing_weeks, normalize PMO tables, and summarize required data-quality review gates.
Generate an overbook/idle/mismatch report for 2026-06-29 to 2026-08-07.
Recommend rebalance options for the highest-risk overbooked member in 07_onboarding_missing_weeks.